TABLE OF CONTENTS

1. Table of contents ………………………………………………………… 1 2. Executive Summary …………………………………………………….. 2 3. Introduction and Background Information ………………………….. 3 4. Planned Activities ……………………………………………………….. 3 - 4 5. Implementation Status ………………………………………………….. 4 - 6 6. Financial Status ………………………………………………………….. 7 7. Problems and Challenges ………………………………………………. 7 - 8 8. Remedial Actions ……………………………………………………….. 8 9. Annex I: Summary of PFG that undergone season long training in FY 2007/08 …………………………………………………………….. 9 10. Annex II: Summary of PFG that undertakes season long training in FY 2008/09 ………………………………………………………….. 10 - 15

EXECUTIVE SUMMARY

About the report

This report narrates the progress of implementation of DASIP for the period from July to December 2008. The report outlines the plan of implementation and proceeds to explain the performance so far realized during the period under review. The report winds up by outlining the problems and challenges faced during implementations and suggest ways of solving them.

Implementation plans

During the period under review, the district planned to implement the following activities as per annual work plan and carried over activities from the FY 2007/08:

- Facilitation of PFGs in opening bank account for implementing economic mini-projects and criteria of selection of those projects.

- Formation of 120 PFGs.

- To conduct season long training to 120 PFGs.

- Training of 26 Farmer Facilitators (FFs) on methodologies/principles of training PFGs.

- To procure 80 Bicycles

- Construction of 3 cattle crushes

- Construction of 2 crop storage facilities

- Construction of 3 watering charco

- Construction of 3 crop storage facilities

- Construction of 4 crop marketing sheds

- Construction of 3 watering charcos

- Construction of 1 slaughter slab

- Construction of rural feeder roads in 2 villages

- Purchase of 1 Cassava processing machine  (chipper)

- Construction of rural road (20 kms) under medium size infrastructure modality

- Monitoring and supervision of village/group micro projects.

Implementation status

The report narrates clearly the implementation status so far reached in each of the planned activities.

Problems and challenges (issues and constraints) and remedial measures

The report highlights the problems and challenges faced during implementation and suggest remedial measures to redress them so as to effect smooth implementation in the future.

- INTRODUCTION AND BACKGROUND INFORMATION

Biharamulo District Council (BDC) is among 28 district councils implementing developmental mini projects/activities by utilizing the funds from the District Agriculture Sector Investment Project (DASIP).

The implementation of the DASIP BDC is in 20 villages as shown in the table below:

| No. | District | Ward | Village |
| --- | --- | --- | --- |
| 1. | Biharamulo | Kalenge | Kasato1 and Ntumagu1 |
|  |  | Nyakahura | Mabare1 and Mihongora1 |
|  |  | Biharamulo Mjini | Musenyi1, Katerela1 and Rugondo1 |
|  |  | Nyarubungo | Nyamahanga1, Ntungamo1, Kabukome1 and Kisuma1 |
|  |  | Nyabusozi | Mbindi1 and Nemba1 |
|  |  | Nyamigogo | Kasozibakaya1 and Kagoma2 |
|  |  | Runazi | Rwekubo2 and Kagondo2 |
|  |  | Lusahunga | Iyengamulilo/Nyantakala2, Kaniha2 and Kasilo2 |

Note: 1 = Village which were implementing DASIP before the split of Biharamulo District into two Districts

of Biharamulo District and Chato District.

2 = Village which were added following the decision of the Government to make up to 20 villages in

each of the newly formed Districts of  Biharamulo, Chato, Bukoba Rural, Missenyi, Tarime and Rorya.

This report explains progress made component – wise, for the FY 2008/09 (i.e it includes carried over activities of FY 2007/2008 and the activities for the FY 2008/09 up to the end of the second quarter (December 31st, 2008 of FY 2008/09). The report also highlights problems and challenges faced during implementations and suggest ways of solving them.

- PLANNED ACTIVITIES

Physical status

Component 1:  Farmers Capacity building component.

The activities planned under this Component for the period under review were:

- Facilitation of PFGs in opening bank account for implementing economic mini-projects and criteria of selection of those projects.

- Formation of 120 PFGs.

- To conduct season long training to 120 PFGs.

- Training of 26 Farmer Facilitators (FFs) on methodologies/principles of training PFGs.

- To procure 80 Bicycles

Component 2: Community planning and Investment in Agriculture

The plan during the period under review was to finalize implementation of carried over activities of FY 2007/08 and semi annual activities of FY 2008/09.

Carried over activities of FY 2007/08 include:-

- Construction of 3 cattle crushes

- Construction of 2 crop storage facilities

- Construction of 3 watering charco

- Monitoring and supervision of village/group micro projects.

Planned activities for the semi annual of FY 2008/09 include:

- Construction of 3 crop storage facilities

- Construction of 4 crop marketing sheds

- Construction of 3 watering charcos

- Construction of 1 slaughter slab

- Construction of rural feeder roads in 2 villages

- Purchase of 1 Cassava processing machine  (chipper)

- Construction of rural road (20 kms) under medium size infrastructure 	modality

- Monitoring and supervision of village/group micro projects.

- IMPLEMENTATION STATUS

Component 1: Farmer capacity building component

- 24 PFGs were facilitated in opening bank account, and their funds Tshs 400,000 for implementing economic mini-projects for each PFG were disbursed through their account. The Ward Training Facilitators (WTFs) are going on monitoring the economic mini-projects in their respective areas.

- Formation of 120 PFGs and Training Needs Assessment were done as scheduled.

- The 120 PFGs are undertaking season long training in different enterprises. The summary of enterprises is attached as annex I

- The Phase one of 4 days training to 26 Farmer Facilitators (FFs) was conducted as scheduled.

- 80 bicycles were procured.

Component 2: Community planning and Investment in Agriculture

Implementation status for Carried over activities of FY 2007/08

The table below depicts the implementation status of the said activities/projects:

| No | Name of Project/Activity | Implementation status | Remarks |
| --- | --- | --- | --- |
| 1. | Construction of 3 cattle crushes at Kasato, Rugondo and Mbindi Villages | Construction has been completed | - |
| 2. | Construction of 2 crop storage facilities at Kasozibakaya and Mabare villages | Construction has been completed | - |
| 3. | Construction of 3 watering charco at Nemba, Ntungamo and Nyamahanga villages | Construction of Nemba watering charco is complete; industrial materials for construction of Nyamahanga and Ntungamo watering charco have been procured | After surveying the sites in Nyamahanga and Ntungamo villages that were meant for construction of watering charcos it was found that were not suitable. Therefore the village authority under the guidance of District Water Engineer decided to construct water gravity schemes. The construction for both sites have stated and will be completed in the 3rd quarter of FY 2008/09 |
| 4. | Monitoring and supervision of village/group micro projects. | This has been done accordingly | - |

Implementation status of planned semi annual activities of FY 2008/09

| No | Name of Project/Activity | Implementation status | Remarks |
| --- | --- | --- | --- |
| 1. | Construction of 3 crop storage facilities at Kasato, Ntumagu and Mihongora villages | Bill of Quantities already prepared Tendering process in progress | - |
| 2. | Construction of 4 crop marketing sheds at Iyengamulilo, Kasilo, Katerela and Musenyi villages | Bill of Quantities already prepared Tendering process in progress | The funds for Musenyi village not yet disbursed |
| 3. | Construction of 3 watering charcos at Kagondo, Rwekubo and Kagoma villages | The construction work for all charcos have already been procured The construction for Rwekubo watering charco is complete | The sites for Kagondo, and Kagoma villages are flooded with water |
| 4. | Construction of 1 slaughter slab at Mabare village | Bill of Quantities already prepared Tendering process in progress | - |
| 5. | Construction of rural feeder roads at Kabukome and Kaniha villages | Preliminary survey has been done for Kabukome road | The funds for Kaniha road not yet disbursed |
| 6. | Purchase of 1 Cassava processing machine (chipper) | Price inquired done |  |
| 7. | Construction of rural road (20 kms) under medium size infrastructure modality | - | - |
| 8. | Monitoring and supervision of village/group micro projects. | Done regularly | - |

- FINANCIAL STATUS

  - Funds received

For the first quarter, financial year 2008/2009 Maswa district council has received Tshs. 34,475,000/= as total budget for the following activities:-

Farmers Capacity building component

  - PFGs investment in economic min-projects Tshs.10,400,000/=

  - Formation of 120 PFGs……………….	Tshs. 	1,600,000/=

  - Motorcycle allowance………………..	 Tshs.     900,000/=

  - DTCs office operation & maintenance ….. Tshs      600,000/=

  - DTCs District staff field allowances…………Tshs      650,000/=

  - Season long training ………………………….Tshs 60,000,000/=

Community planning and Investment in Agriculture

(i) 	Office operation & maintenance………………Tshs.       750,000/=

- DPO &DMEO Motorcycle allowances ……..  Tshs.      900,000/=

- District staff field allowances…………… …     Tshs.    4,375,000/=

- Investment funds to village Microprojects ..   Tshs. 213,910,000/=

Grand total …………………………….Tshs. 283,685,000/=

  - Funds spent as at 31st December, 2008

A total of Tshs 92,238,640/= was spent both for community planning and farmers capacity building components

- PROBLEMS AND CHALLENGES (ISSUES AND CONSTRAINTS)

- Slow pace of community in mobilizing local building materials for construction activities for community mini project investments.

- Slow pace of communities and groups project supervision committees in opening bank accounts for quick implementation of micro projects funded by DASIP.

- Low accountability and irresponsible of village local leaders

- Presence of many socio economic activities such as construction of

dispensaries, secondary schools infrastructures etc that involves the same  community.

- Conflict of interest among community project supervision committees. The typical example is that of community project supervision committee for Rugondo village who hired the contractor who had not qualified during tendering process. This was resolved after summoning the community project supervision committee to judiciary.

- There is no reliable transport in the District. The vehicle that has been used in our day-to-day undertakings is so exhausted, and the policy that fuel (diesel) should come from the DED has to issue is so impossible to implement.  This makes difficult for the DASIP staff to undertake their scheduled activities.

- Farmers Facilitators are not motivated to work, they have been complaining that they are spending their time for activities that are not rewarding.

- REMEDIAL ACTIONS

- To continue sensitize community on the importance of adherence to work plans and enforcement of village by-Laws to laxity community members.

- To continue on educating the community on the importance of implementing their projects within the planed time frame.

- Enforcement of Local government ACT No. 7 of 1982 to non accountable and irresponsible local leaders.

- To continue with educating Local leaders on their responsibilities in development projects.

- To continue educating the project committees on importance of hiring qualified contractors for good quality works

- DASIP Project Coordination Unit to continue negotiating with responsible bodies on the possibility of providing reliable transport facility and allow the district to spent some monies in buying fuel.

- DASIP Project Coordination Unit is requested to find the mechanism of giving incentives to farmer facilitators which can be termed as Bicycle allowances.

ANNEX I:  SUMMARY OF PARTICIPATORY FARMERS GROUP (PFG) THAT UNDERGONE SEASON LONG TRAINING IN FY 2007/08

NAME OF DISTRICT: BIHARAMULO DISTRICT COUNCIL

REPORTING DATE: 31/12/2008                                                                      QUARTER: SEMI-ANNUAL 2008

NAME OF REPORTING OFFICER: Alex Buguzi                                                    YEAR: 2008/2009.

| S/Na | Ward | Name Of Village | Name Of PFG | Year | Number Of Members | Enterprise | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Formed | Graduated | Males | Females | Total |  |  |
| 1. | Nyabusozi | Nemba | Nguvu kazi | 2007 | 2008 | 8 | 5 | 13 | Cotton |  |
|  |  |  | Igembesabo | 2007 | 2008 | 10 | 0 | 10 | Cotton |  |
|  |  | Mbindi | Mapato | 2007 | 2008 | 10 | 5 | 15 | Cotton |  |
|  |  |  | Wakulima | 2007 | 2008 | 9 | 5 | 14 | Cotton |  |
| 2. | Nyamigogo | Kasozibakaya | Tegemeo | 2007 | 2008 | 10 | 7 | 17 | Cassava |  |
|  |  |  | Umoja | 2007 | 2008 | 6 | 10 | 16 | Cotton |  |
| 3. | Nyakahura | Mabare | Gwavya | 2007 | 2008 | 9 | 14 | 23 | Maize |  |
|  |  |  | Mabare chini | 2007 | 2008 | 10 | 14 | 24 | Maize |  |
|  |  | Mihongora | Rugese | 2007 | 2008 | 10 | 9 | 19 | Maize |  |
|  |  |  | Uwanja wa ndege | 2007 | 2008 | 4 | 10 | 14 | Maize |  |
| 4. | Kalenge | Kasato | Muungano | 2007 | 2008 | 6 | 6 | 12 | Cotton |  |
|  |  |  | Tupendane | 2007 | 2008 | 8 | 10 | 18 | Cotton |  |
|  |  | Ntumagu | Upendo | 2007 | 2008 | 10 | 8 | 18 | Cotton |  |
|  |  |  | Juhudi | 2007 | 2008 | 10 | 9 | 19 | Cotton |  |
| 5. | Nyarubungo | Kabukome | Umoja | 2007 | 2008 | 12 | 10 | 22 | Maize |  |
|  |  |  | Kasi mpya | 2007 | 2008 | 10 | 6 | 16 | Maize |  |
|  |  | Nyamahanga | Jitegemee | 2007 | 2008 | 6 | 6 | 12 | Maize |  |
|  |  |  | Umoja | 2007 | 2008 | 5 | 5 | 10 | Maize |  |
|  |  | Ntungamo | Upendo A | 2007 | 2008 | 3 | 5 | 8 | Maize |  |
|  |  |  | Upendo B | 2007 | 2008 | 6 | 4 | 10 | Maize | 7 members have emigrated |
| 6. | Biharamulo mjini | Musenyi | Bidii | 2007 | 2008 | 13 | 10 | 23 | Maize |  |
|  |  |  | Ujamaa | 2007 | 2008 | 5 | 6 | 11 | Maize | 9 members have emigrated |
|  |  | Rugondo | Nguvu kazi | 2007 | 2008 | 10 | 8 | 18 | Maize |  |
|  |  |  | Uzalishaji mali | 2007 | 2008 | 8 | 8 | 16 | Maize |  |
|  |  | Katerela | Mshikamano | 2007 | 2008 | 10 | 7 | 17 | Maize |  |
|  |  |  | Ushirika mafunzo | 2007 | 2008 | 9 | 7 | 16 | Maize |  |
| JUMLA |  |  |  | 217 | 194 | 411 |  |  |

ANNEX II:  SUMMARY OF PARTICIPATORY FARMERS GROUP (PFG) THAT UNDERTAKES SEASON LONG TRAINING IN FY 2008/09

NAME OF DISTRICT: BIHARAMULO DISTRICT COUNCIL

REPORTING DATE: 31/12/2008                                                                      QUARTER: SEMI-ANNUAL 2008

NAME OF REPORTING OFFICER: Alex Buguzi                                                    YEAR: 2008/2009.

| S/No | Ward | Village | Name Of PFG | Number of members | Enterprise | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Male | Female | Total |  |  |
| 1 | Nyabusozi | Nemba | Nemba A | 25 | 0 | 25 | Cotton |  |
|  |  |  | Nemba B | 25 | 0 | 25 | Cotton |  |
|  |  |  | Chakitaragu A | 25 | 0 | 25 | Cotton |  |
|  |  |  | Chakitaragu B | 25 | 0 | 25 | Maize |  |
|  |  |  | Kanugure | 25 | 0 | 25 | Maize |  |
|  |  |  | Shirabera | 25 | 0 | 25 | Cotton |  |
|  |  | Mbindi | Nyakaziba | 17 | 8 | 25 | Maize |  |
|  |  |  | Upendo | 14 | 11 | 25 | Maize |  |
|  |  |  | Umoja | 18 | 7 | 25 | Cotton |  |
|  |  |  | Mwongozo | 20 | 5 | 25 | Cotton |  |
|  |  |  | Maendeleo | 20 | 5 | 25 | Maize |  |
|  |  |  | Mbindi "A" | 19 | 6 | 25 | Cotton |  |
| 2 | Nyamigogo | Kasozibakaya | Igembesabo | 13 | 12 | 25 | Beans |  |
|  |  |  | Maendeleo | 19 | 6 | 25 | Cotton |  |
|  |  |  | Juhudi | 13 | 12 | 25 | Maize |  |
|  |  |  | Tujiendeleze | 12 | 13 | 25 | Maize |  |
|  |  |  | Azimio | 12 | 13 | 25 | Maize |  |
|  |  |  | Ushirikiano | 16 | 9 | 25 | Cotton |  |
|  |  | Kagoma | Twende na wakati | 11 | 9 | 20 | Maize |  |
|  |  |  | Mkombozi | 17 | 8 | 25 | Maize |  |
|  |  |  | Tujikomboe | 12 | 13 | 25 | Maize |  |
|  |  |  | Nguvukazi "A" | 13 | 12 | 25 | Maize |  |
|  |  |  | Majengo | 16 | 8 | 24 | Cotton |  |
|  |  |  | Nguvukazi "B" | 11 | 9 | 20 | Maize |  |

| S/No | Ward | Village | Name Of PFG | Number of members | Enterprise | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Male | Female | Total |  |  |
| 3 | Nyakahura | Mabare | CARE | 13 | 10 | 23 | Maize |  |
|  |  |  | Mzani | 12 | 8 | 20 | Maize |  |
|  |  |  | Mangasini | 6 | 19 | 25 | Maize |  |
|  |  |  | Balimi | 15 | 8 | 23 | Maize |  |
|  |  |  | Mwigabilo | 10 | 11 | 21 | Maize |  |
|  |  |  | Ngazi saba | 9 | 14 | 23 | Maize |  |
|  |  | Mihongora | Mkaragata | 11 | 14 | 25 | Maize |  |
|  |  |  | Songambele | 13 | 12 | 25 | Maize |  |
|  |  |  | Bigufa | 10 | 15 | 25 | Maize |  |
|  |  |  | Jiendeleze | 10 | 15 | 25 | Maize |  |
|  |  |  | Jitihada | 13 | 12 | 25 | Maize |  |
|  |  |  | Tujikomboe | 11 | 14 | 25 | Maize |  |
| 4 | Kalenge | Kasato | Songambele | 13 | 12 | 25 | Beans |  |
|  |  |  | Nguvu kazi | 13 | 12 | 25 | Maize |  |
|  |  |  | Maendeleo | 14 | 11 | 25 | Maize |  |
|  |  |  | Umoja | 13 | 12 | 25 | Beans |  |
|  |  |  | Jitegemee | 13 | 12 | 25 | Maize |  |
|  |  |  | Tuimarike | 13 | 12 | 25 | Maize |  |
|  |  | Ntumagu | Nguvu kazi | 13 | 12 | 25 | Maize |  |
|  |  |  | Tujitume | 12 | 13 | 25 | Cotton |  |
|  |  |  | Jitegemee | 14 | 11 | 25 | Cassava |  |
|  |  |  | Mahusiano | 13 | 12 | 25 | Maize |  |
|  |  |  | Tujikwamue | 17 | 8 | 25 | Maize |  |
|  |  |  | Muungano | 13 | 12 | 25 | Maize |  |

| S/No | Ward | Village | Name Of PFG | Number of members | Enterprise | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Male | Female | Total |  |  |
| 5 | Nyarubungo | Kabukome | Mapambano | 13 | 12 | 25 | Maize |  |
|  |  |  | Maendeleo | 13 | 12 | 25 | Maize |  |
|  |  |  | Upendo | 14 | 11 | 25 | Maize |  |
|  |  |  | Mshikamano | 14 | 11 | 25 | Groundnuts |  |
|  |  |  | Upendano | 13 | 12 | 25 | Rice |  |
|  |  |  | Mtakuja | 13 | 12 | 25 | Maize |  |
|  |  | Nyamahanga | Tuinuane | 14 | 11 | 25 | Maize |  |
|  |  |  | Mshikamano | 15 | 10 | 25 | Maize |  |
|  |  |  | Tusaidiane | 12 | 13 | 25 | Maize |  |
|  |  |  | Tuwajibike | 13 | 12 | 25 | Maize |  |
|  |  |  | Tumaini | 12 | 12 | 24 | Maize |  |
|  |  |  | Tufadhiliwe | 16 | 9 | 25 | Maize |  |
|  |  | Ntungamo | Umoja | 13 | 12 | 25 | Groundnuts |  |
|  |  |  | Tupendane | 10 | 15 | 25 | Beans |  |
|  |  |  | Maendeleo | 13 | 12 | 25 | Maize |  |
|  |  |  | Endelevu | 12 | 13 | 25 | Groundnuts |  |
|  |  |  | Upendo | 19 | 6 | 25 | Groundnuts |  |
|  |  |  | Tuungane | 16 | 9 | 25 | Maize |  |
|  |  | Kisuma | Umoja ni nguvu | 15 | 10 | 25 | Maize |  |
|  |  |  | Tuombe Mungu | 13 | 12 | 25 | Maize |  |
|  |  |  | Ushirika | 13 | 12 | 25 | Maize |  |
|  |  |  | Umoja | 12 | 13 | 25 | Maize |  |
|  |  |  | Igunabahabi | 13 | 12 | 25 | Maize |  |
|  |  |  | Chapa kazi | 15 | 10 | 25 | Maize |  |

| S/No | Ward | Village | Name Of PFG | Number of members | Enterprise | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Male | Female | Total |  |  |
| 6 | Biharamulo mjini | Musenyi | Ushindi | 14 | 11 | 25 | Maize |  |
|  |  |  | Chapa Kazi | 14 | 11 | 25 | Maize |  |
|  |  |  | Muungano | 11 | 14 | 25 | Maize |  |
|  |  |  | Songambele | 10 | 15 | 25 | Maize |  |
|  |  |  | Magezi | 14 | 11 | 25 | Maize |  |
|  |  |  | Tuhwelane | 10 | 4 | 24 | Maize |  |
|  |  | Katerela | Kujikomboa | 13 | 12 | 25 | Maize |  |
|  |  |  | Maendeleo | 12 | 13 | 25 | Maize |  |
|  |  |  | Songambele | 5 | 20 | 25 | Maize |  |
|  |  |  | Tukomboane | 18 | 7 | 25 | Maize |  |
|  |  |  | Kitangalo | 12 | 13 | 25 | Maize |  |
|  |  |  | Nyarusanda | 15 | 10 | 25 | Maize |  |
|  |  | Rugondo | Tweyambe | 17 | 8 | 25 | Maize |  |
|  |  |  | Umoja | 14 | 8 | 22 | Maize |  |
|  |  |  | Ushirikiano | 8 | 15 | 23 | Maize |  |
|  |  |  | Tujiendeleze | 18 | 7 | 25 | Maize |  |
|  |  |  | Tujikusanye | 15 | 10 | 25 | Maize |  |
|  |  |  | Tujitahidi | 7 | 18 | 25 | Maize |  |

| S/No | Ward | Village | Name Of PFG | Number of members | Enterprise | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Male | Female | Total |  |  |
| 7 | Lusahunga | Iyengamulilo/Nyantakala | Muungano | 12 | 13 | 25 | Maize |  |
|  |  |  | Maendeleo | 13 | 12 | 25 | Maize |  |
|  |  |  | Mapinduzi | 13 | 12 | 25 | Maize |  |
|  |  |  | Tukomboane | 13 | 12 | 25 | Maize |  |
|  |  |  | Tujitegemee | 12 | 13 | 25 | Maize |  |
|  |  |  | Igembesabo | 16 | 9 | 25 | Maize |  |
|  |  | Kasilo | Tumaini | 12 | 13 | 25 | Maize |  |
|  |  |  | Maendeleo | 14 | 11 | 25 | Maize |  |
|  |  |  | Mkombozi | 13 | 12 | 25 | Maize |  |
|  |  |  | Millenia | 12 | 13 | 25 | Maize |  |
|  |  |  | Jiendeleze | 13 | 12 | 25 | Maize |  |
|  |  |  | Mshikamano | 16 | 9 | 25 | Maize |  |
|  |  | Kaniha | Juhudi | 12 | 13 | 25 | Maize |  |
|  |  |  | Songambele | 13 | 12 | 25 | Maize |  |
|  |  |  | Umoja | 11 | 14 | 25 | Maize |  |
|  |  |  | Nuru | 12 | 13 | 25 | Beans |  |
|  |  |  | Tujitegemee | 13 | 12 | 25 | Cotton |  |
|  |  |  | Nyota | 12 | 13 | 25 | Maize |  |

| S/No | Ward | Village | Name Of PFG | Number of members | Enterprise | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Male | Female | Total |  |  |
| 8 | Runazi | Kagondo | Umoja | 12 | 13 | 25 | Cotton |  |
|  |  |  | Maendeleo | 13 | 12 | 25 | Cotton |  |
|  |  |  | Hemaro | 12 | 13 | 25 | Maize |  |
|  |  |  | Jipemoyo | 12 | 13 | 25 | Cassava |  |
|  |  |  | Tujiendeleze | 12 | 13 | 25 | Maize |  |
|  |  |  | Nyakaole | 12 | 13 | 25 | Cotton |  |
|  |  | Rwekubo | Upendo | 12 | 13 | 25 | Maize |  |
|  |  |  | Jielimishe | 12 | 13 | 25 | Cassava |  |
|  |  |  | Azimio | 12 | 13 | 25 | Cassava |  |
|  |  |  | Usilale | 12 | 13 | 25 | Maize |  |
|  |  |  | Umoja | 12 | 13 | 25 | Maize |  |
|  |  |  | Maarifa | 12 | 13 | 25 | Maize |  |
| TOTAL | 1,647 | 1,310 | 2,957 |  |  |