# KARAGWE DISTRICT COUNCIL

P.O. BOX 20,

KARAGWE.

REF.NO. KGR/HWK/T.29/26			2 January 2009

Project Coordinator ,

DASIP,

Nyanza Cooperative Union Ltd Building,

3rd Floor,

P.O. Box 11185

MWANZA.

Ref: IMPLEMENTATION PROGRESS REPORT FOR THE SECOND QUARTER

OCTOBER –DECEMBER 2008/09

The above heading refers.

Find herewith attached   DASIP IMPLEMENTATION PROGRESSIVE REPORTSECOND QUARTER 2008/2009.

The report includes

  - General Information & Background.

  - Introduction.

  - Planned Activities

  - Physical performance

  - Financial status

  - Challenges faced

  - Lessons learnt

  - Recommendations

  - Future plans

  - Annex.

C.M. Kamuhabwa

DISTIRICT EXECUTIVE DIRECTOR

KARAGWE DISTRICT COUNCIL

# KARAGWE DISTRICT COUNCIL

DISTRICT AGRICULTURAL DEVELOPMENT PLAN 2008/2009

Implementation report for 2nd  Quarter

OCTOBER-DECEMBER

DASIP

P.O. BOX. 20,						Tel.     028 – 2227140

KARAGWE.							Fax:    028 – 2227148

1.1 General information and Background

Karagwe District is characterized by mountains ranges, which are separated by swampy valley bottoms and wet lands. The altitude ranges between 1500-1800 meters above sea level while valley bottoms and wet lands are 1150 meters to 1450 meters above sea level.

Most of the District has a tropical highland climate. The annual average temperature is 26 0C Rainfall distribution is bi-modal with peak rains from September to December and from March to May. This type of climate makes the District very potential for most of Agricultural crops.

1.2 INTRODUCTION

The government of Tanzania through a loan from the African Development Bank is implementing the District Agriculture sector Investment Project (DASIP).The Project aims at increasing productivity and income of the rural households in the project area within a frame work of the Agriculture Sector Development Strategy (ASDS).The project will be implemented over a period of six years starting from January 2006.

It will cover a total of 30 villages in 20 wards. Project components are;

- Farmers capacity Building.

- Community planning and investment in Agriculture.

- Support to Rural financial services and marketing.

- Project coordination and management.

Karagwe District Council in collaboration with other stakeholders is implementing Agricultural Sector Development Programme (ASDP) through its District Agricultural Development Plan (DADP). The Council is receiving grants from the Central Government and Other donors for the development of the Agriculture sector. DASIP being part of DADPs is receiving grants from AfDB to implement different activities including Community Planning &Investment projects, Farmers capacity building as well as Marketing and Micro financial services.

2.0 PLANNED ACTIVITIES

Different activities have been planned to be implemented this year as shown in the list below starting with carried forward activities.

Activities planned in 2007/08

Community Planning and Investment in Agriculture

- To construct 1 cattle dip at Kyerere village.

- To construct 1 cattle dip at Bujuruga village.

- To construct 1 char co dam at Nyakagoyagoye village.

- To rehabilitate 5 km of feeder roads at Kihinda village.

- To rehabilitate 4 km of feeder road at Masheshe village.

Farmers capacity Building

- To train 60 participatory farmer groups (PFGs).

- To train 30 participatory farmer supervision committees (PFSCs).

- To train 24 ward training facilitators (WTFs).

- Annual follow up training in O&OD methods.

Activities planned in 2008/09

Community Planning and Investment in Agriculture

- To construct 8 storage facilities.

- To construct 6 water troughs.

- To construct 3 permanent cattle crushes.

- To rehabilitate 1 slaughter slab.

- To purchase 6 coffee hullers.

- To establish large irrigation scheme in the district.

- To construct one fish pond.

- To rehabilitate 11 km of feeder roads and 3 culverts.

- To purchase 240,000 of cassava cuttings.

- To purchase 200 piglets.

- To support 60 participatory farmer groups on micro-project investments.

Farmers capacity Building

- To train 180 Participatory farmer groups.

- To train Farmer facilitators.

- To continue train PFG’s supervision committees.

- To continue train Ward training facilitators.

3.0 Physical performances

Funds for planned activities have been disbursed to respective villages through their Bank accounts.

The last year’s groups have continued with implementation of their projects. Formation of new Groups, four in each village is completed; appointment of leadership; Bank account opening and other necessary procedures are being performed. Groups formed so far are as indicated in Annex 6

4.0 FINANCIAL STATUS

Community & group projects have been supported especially those which commenced in 2007/08. Newly found groups will be supported this financial year. Financial position of group community projects are as shown in Annex 1, 2 & 4

5.0 CHALLENGES FACED

With all efforts endeavored still we are facing some challenges in the due course of implementation. Major ones being;

- Slow response in implementing project activities by villages.

- BOQ not timely prepared.

- Slow rate of local community contribution.

- Little amount of money allocated for supervision to DTCs.

- Lack of transport like a car hinders quick response of officers to supervise activities in the field.

- Lack of funds allocated for fuels.

- Poor understanding of supervision committee members and other village leaders.

6.0 LESSONS LEARNT

- The project should have its vehicle at District level for smooth learning of activities.

- Fuel cost should be incorporated in project funds.

- More sensitization to the society is needed to have community contribution at the required time.

7.0 RECOMMENDATIONS

- More staff is needed at village level to make sure farmers are technically supported accordingly.

- Village supervision committees need regular training especially in the initial stages of project implementation.

8.0 FUTURE PLANS

  - Completion of previous year projects.

  - Implement this year projects as scheduled.

  - More concentration on project activities for all focal persons.

  - Continue sensitizing community on contribution of projects.

# CARRIED FORWARD COMMUNITY INVESTMENT PROJECTS

# Name of District: KARAGWE

Reporting Date:  2 Jan, 2009  					               Quarter:  SECOND

Name of Reporting Officer:  Samuel Stambuli                        		  Financial year: 2008/09

Annex. 1

| Village | Number of Households | Investment Type | Project Cost | Remarks |
| --- | --- | --- | --- | --- |
|  |  |  | Total(Tshs) | Contributions by Source |  |
|  |  |  |  | Community | DASIP |  |
|  |  |  |  |  | Total | Disbursed | Balance | Unallocated |  |
| KYERERE | 521` | Construction of Cattle dip | 16,000,000 | 3,200,000 | 12,800,000 | 12,800,000 | - | - | Changed the project to godown |
| BUJURUGA | 415 | Construction of Cattle dip | 16,000,000 | 3,200,000 | 12,800,000 | 12,800,000 | - | - | Tender advertisement |
| NYAKAGOYAGOYE | 916 | Construction of Char co dam | 16,000,000 | 3,200,000 | 12,800,000 | 12,800,000 | - | - | BOQ preparation |
| MASHESHE | 709 | Rehabilitation of 4 km of feeder roads | 4,800,000 | 960,000 | 3,840,000 | 3,840,000 | - | - | Completed |
| KIHINDA | 595 | Rehabilitation of 5 km of feeder roads | 6,000,000 | 1,200,000 | 4,800,000 | 4,800,000 | - | - | Completed |
| TOTAL | 2635 |  | 58,800,000 | 11,760,000 | 47,040,000 | 47,040,000 |  |  |  |

# SUMMARY OF COMMUNITY INVESTMENT PROJECTS

# Name of District: KARAGWE

Reporting Date:  2 Jan, 2009  					               Quarter; SECOND

Name of Reporting Officer:  Samuel Stambuli                        		  Financial year: 2008/09

Annex. 2

| Village | Number of Households | Investment Type | Project Cost | Remarks |
| --- | --- | --- | --- | --- |
|  |  |  | Total(Tshs) | Contributions by Source |  |
|  |  |  |  | Community | DASIP |  |
|  |  |  |  |  | Total | Disbursed | Balance | Unallocated |  |
| KYERERE | 521 | Purchase of two coffee hullers | 15,000,000 | 7,500,000 | 7,500,000 | - | - | - | Not received |
| KITWE | 795 | Rehabilitation of 2 km feeder road | 22,000,000 | 4,400,000 | 17,600,000 | - | - | - | Not received |
| KIBIMBA | 991 | Purchase two coffee hullers | 15,000,000 | 7,500,000 | 7,500,000 | - | - | - | Not received |
| BUSINDE | 830 | Construction of permanent clash | 7,000000 | 1,400,000 | 5,600,000 | - | - | - | Tender in process |
| ITEERA | 971 | Establishment of cassava farms (10 ha) | 500,000 | 100,000 | 400,000 | - | - | - | Not received |
| RWABWERE | 762 | Godown construction | 25,000,000 | 5,000,000 | 20,000,000 | - | - | - | Tender in process |
| KIHANGA | 577 | Improved Pig production | 2,000,000 | 400,000 | 1,600,000 | - | - | - | Not received |
| KATERA | 844 | Godown construction | 25,000,000 | 5,000,000 | 20,000,000 | - | - | - | Tender in process |
| KIBONA | 509 | Godown construction | 25,000,000 | 5,000,000 | 20,000,000 | - | - | - | Tender in process |
| IGURWA | 317 | Road rehabilitation | 11,000,000 | 2,200,000 | 8,800,000 | - | - | - | Tender in process |
| MASHESHE | 709 | Road rehabilitation | 22,000,000 | 4,400,000 | 17,600,000 | - | - | - | Not received |
| KAYANGA | 2096 | Rehabilitation of slaughter slab | 20,000,000 | 4,000,000 | 16,000,000 | - | - | - | Tender in process |
| CHAMCHUZI | 1825 | Construction of 3 water troughs | 9,000,000 | I,800,000 | 7,200,000 | - | - | - | Tender in process |
| KAKURAIJO | 594 | Godown construction | 25,000,000 | 5,000,000 | 20,000,000 | - | - | - | Tender in process |
| KIBONDO | 484 | Godown construction | 25,000,000 | 5,000,000 | 20,000,000 | - | - | - | Tender in process |
| IHEMBE II | 395 | Construct permanent crush | 7,000,000 | 1,400,000 | 5,600,000 | - | - | - | Tender in process |
|  |  | Rehabilitation of culvert | 6,000,000 | 1,200,000 | 4,800,000 | - | - | - | Tender in process |
| NYABIYONZA | 761 | Godown construction | 25,000,000 | 5,000,000 | 20,000,000 | - | - | - | Tender in process |
| BUKANGARA | 353 | Construct three water troughs | 9,000,000 | 1,800,000 | 7,200,000 | - | - | - | Tender in process |
| NYAKAKIKA | 2337 | Establish medium scale Irrigation Scheme | 225,000,000 | 45,000,000 | 180,000,000 | - | - | - | Not received |
| KAYUNGU | 797 | Road rehabilitation | 11,000,000 | 2,200,000 | 8,800,000 | - | - | - | Tender in process |
| KIHINDA | 595 | Construction of one fish pond | 20,000,000 | 4,000,000 | 16,000,000 | - | - | - | Not received |
| KIBINGO | 1095 | Rehabilitation of two km feeder road | 22,000,000 | 4,400,000 | 17,600,000 | - | - | - | Not received |
| NYAKAGOYAGOYE | 916 | Purchase two coffee hullers | 15,000,000 | 7,500,000 | 7,500,000 | - | - | - | Not received |
|  |  | Establishment of cassava farms (10 ha) | 500,000 | 100,000 | 400,000 | - | - | - | Not received |
| BUJURUGA | 415 | Godown construction | 25,000,000 | 5,000,000 | 20,000,000 | - | - | - | Tender in process |
| LUKALE | 264 | Rehabilitate one culvert | 6,000,000 | 1,200,000 | 4,800,000 | - | - | - | Tender in process |
| NYAKAYANJA | 757 | Rehabilitate one culvert | 6,000,000 | 1,200,000 | 4,800,000 | - | - | - | Tender in process |
| NYABWEGIRA | 538 | Rehabilitate two kms of feeder road | 22,000,000 | 4,400,000 | 17,600,000 | - | - | - | Not received |
| OMURUSIMBI | 343 | Godown construction | 25,000,000 | 5,000,000 | 20,000,000 | - | - | - | Tender in process |
| BUJARA | 343 | Rehabilitate two kms of feeder road | 22,000,000 | 4,400,000 | 17,600,000 | - | - | - | Not received |
| NYAMIYAGA | 1078 | Establishment of SACCOs premises | 10,000,000 | 5,000,000 | 5,000,000 | - | - | - | Not received |
| TOTAL | 23812 |  | 705,000,000 | 108,800,000 | 547,500,000 |  |  |  |  |

# DISTRICT AGRICULTURAL SECTOR INVESTMEN T PROJECT (DASIP)

DISTRICT SUMMARY FOR PARTICIPATORY FARMER GROUPS (PFG)

NAME OF DISTRICT: KARAGWE					            QUARTER ; SECOND

REPORTING DATE: 2 Jan, 2009						YEAR: 2008/09

# NAME OF REPORTING OFFICER: SAMUEL STAMBULI

# Annex. 3

| WARD | VILLAGE | NAME OF PFG | YEAR | NUMBER OF MEMBERS | ENTERPRISE | REMARKS |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | FORMED | GRADUATED | Male | Female | Total |  |  |
| KAMULI | KYERERE | JUHUDI | 2007/08 | NOT GRADUATED | 10 | 15 | 25 | Improved Banana production | Under operation |
|  |  | BARAKA | 2007/08 | GRADUATED | 16 | 9 | 25 | Resistant cassava production | - |
|  | KITWE | NYOTA | 2007/08 | GRADUATED | 14 | 11 | 25 | Improved coffee production | - |
|  |  | MAENDELEO | 2007/08 | NOT GRADUATED | 23 | 2 | 25 | Improved banana production | Under operation |
| MABIRA | KIBIMBA | NYABIHARA | 2007/08 | GRADUATED | 17 | 8 | 25 | Improved maize production | - |
|  |  | KIBIMBA “A” | 2007/08 | NOT GRADUATED | 10 | 15 | 25 | Improved Banana production | Under operation |
|  | BUSINDE | MSHIKAMANO | 2007/08 | GRADUATED | 23 | 2 | 25 | Improved coffee production | - |
|  |  | NYARUGONGO | 2008/08 | GRADUATED | 21 | 4 | 25 | Improved maize production | - |
| RWABWERE | ITEERA | RUKIKI | 2007/08 | GRADUATED | 11 | 14 | 25 | Maize Production | - |
|  |  | UPENDO | 2007/08 | GRADUATED | 15 | 10 | 25 | Maize Production | - |
|  | RWABWERE | NYANGOYE | 2007/08 | GRADUATED | 14 | 11 | 25 | Improved maize production | - |
|  |  | UWAKAKI | 2007/08 | GRADUATED | 16 | 9 | 25 | Horticultural crop production | - |
| ISINGIRO | KIHANGA | JUHUDI | 2007/08 | GRADUATED | 15 | 10 | 25 | Improved coffee production | - |
|  |  | MUUNGANO | 2007/08 | NOT GRADUATED | 13 | 12 | 25 | Improved Banana production | Under operation |
|  | KATERA | TUPENDANE | 2007/08 | NOT GRADUATED | 13 | 12 | 25 | Improved Banana production | Under operation |
|  |  | NEEMA | 2007/08 | GRADUATED | 0 | 25 | 25 | Improved coffee production | - |
| IGURWA | KIBONA | UJAMAA | 2007/08 | NOT GRADUATED | 25 | 7 | 32 | Improved Banana production | Under operation |
|  |  | TUMAINI | 2007/08 | GRADUATED | 20 | 13 | 33 | Improved Beans production | - |
|  | IGURWA | FAIDA | 2007/08 | GRADUATED | 20 | 10 | 30 | Improved Beans production | - |
|  |  | LENGO LETU | 2007/08 | GRADUATED | 22 | 8 | 30 | Improved coffee production | - |
| MURONGO | MASHESHE | MGOMBA | 2007/08 | NOT GRADUATED | 14 | 11 | 25 | Improved Banana production | Under operation |
|  |  | USHIRIKA | 2007/08 | NOT GRADUATED | 16 | 9 | 25 | Improved coffee production | Under operation |
| KAYANGA | KAYANGA | UMOJA NSHESHE | 2007/08 | GRADUATED | 22 | 10 | 32 | Improved coffee production | - |
|  |  | RWAMBALE | 2007/08 | NOT GRADUATED | 15 | 15 | 30 | Improved poultry production | Under operation |
| BWERANYANGE | CHAMCHUZI | UMOJA | 2007/08 | GRADUATED | 11 | 13 | 24 | Improved coffee production | - |
|  |  | TEGEMEO | 2007/08 | GRADUATED | 16 | 8 | 24 | Improved cassava production | - |
| KIBONDO | KAKURAIJO | UWAKAKA | 2007/08 | NOT GRADUATED | 12 | 13 | 25 | Improved Banana production | Under operation |
|  |  | JUHUDI | 2007/08 | NOT GRADUATED | 11 | 14 | 25 | Improved poultry production | Under operation |
|  | KIBONDO | UKIKIA | 2007/08 | NOT GRADUATED | 17 | 8 | 25 | Improved Banana production | Under operation |
|  |  | MAENDELEO | 2007/08 | NOT GRADUATED | 16 | 9 | 25 | Improved Banana production | Under operation |
| IHEMBE | IHEMBE II | MAHAGE | 2007/08 | GRADUATED | 10 | 15 | 25 | Improved poultry production | - |
|  |  | UMANO | 2007/08 | NOT GRADUATED | 18 | 6 | 24 | Tree seedling nursery | Under operation |
| NYABIYONZA | NYABIYONZA | KAYANGO | 2007/08 | GRADUATED | 17 | 8 | 25 | Improved maize production | - |
|  |  | JITEGEMEE | 2007/08 | GRADUATED | 16 | 9 | 25 | Improved coffee production | - |
|  | BUKANGARA | NYOTA | 2007/08 | NOT GRADUATED | 17 | 8 | 25 | Improvement of goat production | Under operation |
|  |  | NYABIRIZI | 2007/08 | NOT GRADUATED | 18 | 7 | 25 | Tree seedling nursery | Under operation |
| NYAKAKIKA | NYAKAKIKA | TUINUANE | 2007/08 | GRADUATED | 16 | 9 | 25 | Improved maize production | - |
|  |  | TWEYAMBE | 2007/08 | GRADUATED | 17 | 9 | 26 | Improved poultry production | - |
|  | KAYUNGU | UPENDO | 2007/08 | GRADUATED | 18 | 7 | 25 | Improved Banana production | - |
|  |  | BORESHA | 2007/08 | GRADUATED | 18 | 7 | 25 | Improved maize production | - |
| KIBINGO | KIBINGO | TUINUANE | 2007/08 | GRADUATED | 13 | 12 | 25 | Diary zero grazing | - |
|  |  | TUSAIDIANE | 2007/08 | GRADUATED | 14 | 11 | 25 | Vegetable production | - |
|  | KIHINDA | JUHUDI | 2007/08 | GRADUATED | 13 | 17 | 30 | Maize production | - |
|  |  | ABAGAMBAKAMO | 2007/08 | GRADUATED | 16 | 14 | 30 | Maize production | - |
| KIRURUMA | NYAKAGOYAGOYE | MUUNGANO | 2007/08 | GRADUATED | 13 | 12 | 25 | Improved Banana production | - |
|  |  | MAPAMBANO | 2007/08 | GRADUATED | 16 | 9 | 25 | Improved coffee production | - |
| BUGENE | BUJURUGA | KIJIUMA | 2007/08 | GRADUATED | 14 | 11 | 25 | Improved Banana production | - |
|  |  | TUKOMBOANE | 2007/08 | GRADUATED | 16 | 9 | 25 | Improved maize production | - |
| NYAISHOZI | NYAKAYANJA | UMOJA NI NGUVU | 2007/08 | GRADUATED | 26 | 12 | 38 | Vegetable production | - |
|  |  | MSHIKAMANO | 2007/08 | GRADUATED | 4 | 16 | 20 | Improved poultry production | - |
|  | LUKALE | OMURWERE | 2007/08 | NOT GRADUATED | 19 | 8 | 27 | Improved Diary Goat production | - |
|  |  | NGUVUKAZI | 2007/08 | GRADUATED | 16 | 13 | 29 | Carrot Production | - |
| NDAMA | NYABWEGIRA | NYAKIRU | 2007/08 | GRADUATED | 14 | 11 | 25 | Improved Banana production | - |
|  |  | UWAWANYA | 2007/08 | GRADUATED | 13 | 12 | 25 | Diary zero grazing | - |
| NYAKAHANGA | OMURUSIMBI | MKOMBOZI | 2007/08 | GRADUATED | 14 | 11 | 25 | Improved maize production | - |
|  |  | PAMAO | 2007/08 | GRADUATED | 15 | 10 | 25 | Improved poultry production | - |
| NYAKASIMBI | BUJARA | JIKOMBOE | 2007/08 | GRADUATED | 12 | 12 | 24 | Improved Beans production | - |
|  |  | JUHUDI | 2007/08 | GRADUATED | 14 | 10 | 24 | Vegetable production | - |
| BUGOMORA | NYAMIYAGA | MWANAKWETU | 2007/08 | NOT GRADUATED | 13 | 12 | 25 | Improved poultry production | Under operation |
|  |  | UMOJA | 2007/08 | NOT GRADUATED | 14 | 11 | 25 | Improved Banana production | Under operation |
| TOTAL OF MEMBERS |  |  | 922 | 635 | 1557 |  |  |

# DISTRICT AGRICULTURAL SECTOR INVESTMENT PROJECT (DASIP)

# FINANCIAL STATUS OF PARTICIPATORY FARMER GROUPS (PFGs)

NAME OF DISTRICT: KARAGWE						QUARTER; SECOND

REPORTING DATE: 2 Jan 2009						YEAR: 2008/09

# NAME OF REPORTING OFFICER: SAMUEL STAMBULI

# Annex 4

| Village | Number of PFG Members | Type of Enterprise | Total Cost (Tsh. ‘000) | Group Contribution (Tsh. ‘000) | Contribution from DASIP (Tsh. ‘000) | Balance (Tsh. ‘000) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Total | Disbursed | Balance | Unallocated |  |
|  | Male | Female | Total |  |  |  |  |  |  |  |  |
| KYERERE | 10 | 15 | 25 | Improved Banana production | 1200 | 700 | 500 | 500 | 0 | 0 | 0 |
|  | 16 | 9 | 25 | Resistant cassava production | 800 | 300 | 500 | 500 | 0 | 0 | 0 |
| KITWE | 14 | 11 | 25 | Improved coffee production | 1300 | 900 | 500 | 500 | 0 | 0 | 0 |
|  | 23 | 2 | 25 | Improved banana production | 900 | 400 | 500 | 500 | 0 | 0 | 0 |
| KIBIMBA | 17 | 8 | 25 | Improved maize production | 900 | 400 | 500 | 500 | 0 | 0 | 0 |
|  | 10 | 15 | 25 | Improved Banana production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| BUSINDE | 23 | 2 | 25 | Improved coffee production | 1300 | 800 | 500 | 500 | 0 | 0 | 0 |
|  | 21 | 4 | 25 | Improved maize production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| ITEERA | 11 | 14 | 25 | Improved Banana production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 15 | 10 | 25 | Improved poultry production | 1200 | 800 | 400 | 400 | 0 | 0 | 0 |
| RWABWERE | 14 | 11 | 25 | Improved maize production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 16 | 9 | 25 | Vegetable production | 950 | 450 | 500 | 500 | 0 | 0 | 0 |
| KIHANGA | 15 | 10 | 25 | Improved coffee production | 1100 | 600 | 500 | 500 | 0 | 0 | 0 |
|  | 13 | 12 | 25 | Improved Banana production | 900 | 500 | 400 | 400 | 0 | 0 | 0 |
| KATERA | 13 | 12 | 25 | Improved Banana production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 15 | 10 | 25 | Improved coffee production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| KIBONA | 25 | 7 | 32 | Improved Banana production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 20 | 13 | 33 | Improved Beans production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| IGURWA | 21 | 11 | 32 | Diary zero grazing | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 22 | 9 | 31 | Improved coffee production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| MASHESHE | 14 | 11 | 25 | Improved Banana production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 16 | 9 | 25 | Improved coffee production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| NYAMIYAGA | 13 | 12 | 25 | Improved poultry production | 1100 | 600 | 500 | 500 | 0 | 0 | 0 |
|  | 14 | 11 | 25 | Improved Banana production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| BUJARA | 12 | 12 | 24 | Improved beans production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 14 | 10 | 24 | Vegetable production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| OMURUSIMBI | 14 | 11 | 25 | Improved maize production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 15 | 10 | 25 | Improved poultry production | 900 | 500 | 400 | 400 | 0 | 0 | 0 |
| NYABWEGIRA | 14 | 11 | 25 | Improved Banana production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 13 | 12 | 25 | Diary zero grazing | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| LUKALE | 19 | 8 | 27 | Improved Banana production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 16 | 13 | 29 | Improved coffee production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| NYAKAYANJA | 26 | 12 | 38 | Vegetable production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 4 | 16 | 20 | Maize Production | 900 | 500 | 400 | 400 | 0 | 0 | 0 |
| KAYANGA | 22 | 10 | 32 | Improved coffee production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 15 | 15 | 30 | Improved poultry production | 900 | 400 | 500 | 500 | 0 | 0 | 0 |
| CHAMCHUZI | 11 | 13 | 24 | Improved coffee production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 16 | 8 | 24 | Improved cassava production | 1200 | 700 | 500 | 500 | 0 | 0 | 0 |
| KAKURAIJO | 12 | 13 | 25 | Improved banana production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 11 | 14 | 25 | Improved poultry production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| KIBONDO | 17 | 8 | 25 | Improved banana production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 16 | 9 | 25 | Improved banana production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| IHEMBE II | 10 | 15 | 25 | Improved poultry production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 18 | 6 | 24 | Tree nursery | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| NYABIYONZA | 17 | 8 | 25 | Improved coffee production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 16 | 9 | 25 | Improved maize production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| BUKANGARA | 17 | 8 | 25 | Diary goat production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 18 | 7 | 25 | Tree nursery production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| NYAKAKIKA | 16 | 9 | 25 | Improved maize production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 17 | 9 | 26 | Improved poultry production | 900 | 500 | 400 | 400 | 0 | 0 | 0 |
| KAYUNGU | 18 | 7 | 25 | Improved banana production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 18 | 7 | 25 | Improved maize production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| KIBINGO | 13 | 12 | 25 | Diary zero grazing | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 14 | 11 | 25 | Vegetable production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| KIHINDA | 13 | 17 | 30 | Improved maize production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 16 | 14 | 30 | Improved maize production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| NYAKAGOYAGOYE | 13 | 12 | 25 | Improved banana production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 16 | 9 | 25 | Improved coffee production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
| BUJURUGA | 14 | 11 | 25 | Improved banana production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  | 16 | 9 | 25 | Improved maize production | 1000 | 500 | 500 | 500 | 0 | 0 | 0 |
|  |  |  |  |  | 60,450 | 31,050 | 29,500 | 29,500 |  |  |  |

# DISTRICT AGRICULTURAL SECTOR INVESTMENT PROJECT (DASIP)

# DISTRICT SUMMARY FOR ALL PROJECTS

NAME OF DISTRICT: KARAGWE				                                                             QUARTER: SECOND

REPORTING DATE: 2 Jan 2009					                                              YEAR: 2008/09.

# NAME OF REPORTING OFFICER: SAMUEL STAMBULI

# Annex 5

| Type of Project and its Description | Number of Projects | Total |
| --- | --- | --- |
|  | Community Investment | Group |  |
| Improved Livestock Husbandry – Improved goat and Diary zero grazing, Improved piggery and poultry keeping, cattle dips construction and rehabilitation, water troughs, slaughter slabs, cattle crushes. | 8 | 11 | 19 |
| Improved Crop Husbandry- Improved Banana production, Improved Cassava resistant varieties production, Improved Maize production, Improved Coffee production, Improved Beans production, Improved horticultural crops production and Tree nursery establishment. | 2 | 49 | 51 |
| Improved Post-harvest technique- Storage facilities construction, Coffee value added equipments, | 11 | 0 | 11 |
| Improved Rural Infrastructure- Improved feeder roads and culverts, Construction of char co dam &fish pond, Established irrigation scheme | 13 | 0 | 13 |
| Total | 34 | 60 | 94 |

# DISTRICT AGRICULTURAL SECTOR INVESTMEN T PROJECT (DASIP)

DISTRICT SUMMARY FOR PARTICIPATORY FARMER GROUPS (PFG)

NAME OF DISTRICT: KARAGWE		     					QUARTER: SECOND

REPORTING DATE: 2 Jan 2009						YEAR: 2008/09

# NAME OF REPORTING OFFICER: SAMUEL STAMBULI

# Annex 6

| WARD | VILLAGE | NAME OF PFG | YEAR | NUMBER OF MEMBERS | ENTERPRISE | REMARKS |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | FORMED | GRADUATED | Male | Female | Total |  |  |
| KAMULI | KYERERE | KUJITEGEMEA | 2008/09 | NEW | 15 | 11 | 26 | Banana Production | Newly formed |
|  |  | MUUNGANO | 2008/09 | NEW | 16 | 9 | 25 | Maize production | Newly formed |
|  |  | MAFANIKIO | 2008/09 | NEW | 14 | 10 | 24 | Maize production | Newly formed |
|  |  | TWEYAMBE | 2008/09 | NEW | 19 | 11 | 30 | Maize production | Newly formed |
|  | KITWE | MAENDELEO | 2008/09 | NEW | 15 | 9 | 24 | Banana Production | Newly formed |
|  |  | NYOTA | 2008/09 | NEW | 16 | 13 | 29 | Horticulture Crop Prod. | Newly formed |
|  |  | KWETU | 2008/09 | NEW | 13 | 12 | 25 | Goat production | Newly formed |
|  |  | TUJENGANO | 2008/09 | NEW | 15 | 11 | 26 | Poultry production | Newly formed |
| MABIRA | KIBIMBA | TWEMANYE | 2008/09 | NEW | 16 | 9 | 25 | Banana Production | Newly formed |
|  |  | SONGAMBELE | 2008/09 | NEW | 18 | 8 | 26 | Maize production | Newly formed |
|  |  | USHIRIKA | 2008/09 | NEW | 14 | 11 | 25 | Poultry Production | Newly formed |
|  |  | TUSAIDIANE | 2008/09 | NEW | 18 | 9 | 27 | Coffee Production | Newly formed |
|  | BUSINDE | KAZI KWETU | 2008/09 | NEW | 16 | 8 | 24 | Banana Production | Newly formed |
|  |  | JUHUDI | 2008/09 | NEW | 17 | 9 | 26 | Poultry Production | Newly formed |
|  |  | MAVUNO | 2008/09 | NEW | 15 | 7 | 22 | Maize production | Newly formed |
|  |  | MAJARIWA | 2008/09 | NEW | 11 | 14 | 25 | Beans production | Newly formed |
| RWABWERE | ITEERA | AKILIMALI | 2008/09 | NEW | 18 | 9 | 27 | Maize production | Newly formed |
|  |  | UJAMAA | 2008/09 | NEW | 10 | 14 | 24 | Beans production | Newly formed |
|  |  | MAFANIKIO | 2008/09 | NEW | 14 | 13 | 27 | Maize production | Newly formed |
|  |  | TUELEKEZANE | 2008/09 | NEW | 16 | 10 | 26 | Banana Production | Newly formed |
|  | RWABWERE | MUUNGANO | 2008/09 | NEW | 18 | 9 | 27 | Horticulture Crop Prod. | Newly formed |
|  |  | AZIMIO | 2008/09 | NEW | 16 | 9 | 25 | Banana Production | Newly formed |
|  |  | MAFANIKIO | 2008/09 | NEW | 13 | 14 | 27 | Horticulture Crop Prod. | Newly formed |
|  |  | MAPINDUZI | 2008/09 | NEW | 18 | 7 | 25 | Banana Production | Newly formed |
| ISINGIRO | KIHANGA | UPENDO | 2008/09 | NEW | 15 | 6 | 21 | Poultry Production | Newly formed |
|  |  | HEKIMA | 2008/09 | NEW | 15 | 10 | 25 | Coffee Production | Newly formed |
|  |  | MAENDELEO KIJARWE | 2008/09 | NEW | 14 | 15 | 25 | Banana Production | Newly formed |
|  |  | FARAJA | 2008/09 | NEW | 7 | 9 | 16 | Coffee Production | Newly formed |
|  | KATERA | MAARIFA | 2008/09 | NEW | 8 | 3 | 11 | Banana Production | Newly formed |
|  |  | TUPENDANE | 2008/09 | NEW | 13 | 11 | 24 | Tomato production | Newly formed |
|  |  | TUJIINUE | 2008/09 | NEW | 12 | 3 | 15 | Goat production | Newly formed |
|  |  | AKINA MAMA NA MAENDELEO | 2008/09 | NEW | 0 | 18 | 18 | Poultry production | Newly formed |
| IGURWA | KIBONA | UJAMAA | 2008/09 | NEW | 14 | 7 | 21 | Poultry production | Newly formed |
|  |  | TUMAINI | 2008/09 | NEW | 5 | 7 | 12 | Maize production | Newly formed |
|  |  | WEKEZA | 2008/09 | NEW | 18 | 9 | 27 | Beans production | Newly formed |
|  |  | UKOMBOZI | 2008/09 | NEW | 10 | 5 | 15 | Maize production | Newly formed |
|  | IGURWA | TWENDENI | 2008/09 | NEW | 15 | 10 | 25 | Beans production | Newly formed |
|  |  | TUSHIRIKIANE | 2008/09 | NEW | 18 | 8 | 26 | Banana Production | Newly formed |
|  |  | RWAMBAIZI | 2008/09 | NEW | 11 | 15 | 26 | Banana Production | Newly formed |
|  |  | MTU KWAO | 2008/09 | NEW | 17 | 7 | 24 | Maize Production | Newly formed |
| MURONGO | MASHESHE | MWONGOZO | 2008/09 | NEW | 14 | 15 | 29 | Maize Production | Newly formed |
|  |  | MWOKOZI | 2008/09 | NEW | 12 | 14 | 26 | Banana Production | Newly formed |
|  |  | FANIKISHA | 2008/09 | NEW | 17 | 9 | 26 | Coffee Production | Newly formed |
|  |  | VUMILIA | 2008/09 | NEW | 12 | 13 | 25 | Poultry production | Newly formed |
| WARD | VILLAGE | NAME OF PFG | YEAR | NUMBER OF MEMBERS | ENTERPRISE | REMARKS |
|  |  |  | FORMED | GRADUATED | Male | Female | Total |  |  |
| KAYANGA | KAYANGA | RUZINGA | 2008/09 | NEW | 4 | 14 | 18 | Maize production | Newly formed |
|  |  | UMOJA NI NGUVU | 2008/09 | NEW | 16 | 9 | 25 | Beans production | Newly formed |
|  |  | OMUKATOMA GROUP | 2008/09 | NEW | 14 | 12 | 26 | Poultry production | Newly formed |
|  |  | ELIMISHA | 2008/09 | NEW | 18 | 9 | 27 | Bean Production | Newly formed |
| BWERANYANGE | CHAMCHUZI | TUKUMBUKANE | 2008/09 | NEW | 7 | 9 | 16 | Maize production | Newly formed |
|  |  | JITIHADA | 2008/09 | NEW | 8 | 3 | 11 | Beans production | Newly formed |
|  |  | WEKEZA | 2008/09 | NEW | 13 | 11 | 24 | Maize production | Newly formed |
|  |  | AZIMIA | 2008/09 | NEW | 12 | 3 | 15 | Beans production | Newly formed |
| KIBONDO | KAKURAIJO | TEGEMEO | 2008/09 | NEW | 0 | 18 | 18 | Maize production | Newly formed |
|  |  | JIKOMBOE | 2008/09 | NEW | 14 | 10 | 24 | Beans production | Newly formed |
|  |  | MWANGAZA | 2008/09 | NEW | 19 | 11 | 30 | Maize production | Newly formed |
|  |  | TUJENGE | 2008/09 | NEW | 15 | 9 | 24 | Beans production | Newly formed |
|  | KIBONDO | UJASIRIAMALI | 2008/09 | NEW | 16 | 13 | 29 | Banana Production | Newly formed |
|  |  | TUSHEMERERWE | 2008/09 | NEW | 7 | 9 | 16 | Bean Production | Newly formed |
|  |  | TULIZA | 2008/09 | NEW | 8 | 3 | 11 | Banana Production | Newly formed |
|  |  | ZALISHA | 2008/09 | NEW | 7 | 9 | 16 | Bean Production | Newly formed |
| IHEMBE | IHEMBE II | MAENDELEO | 2008/09 | NEW | 8 | 3 | 11 | Beans production | Newly formed |
|  |  | HEKIMA | 2008/09 | NEW | 13 | 11 | 24 | Poultry production | Newly formed |
|  |  | MAPINDUZI | 2008/09 | NEW | 12 | 3 | 15 | Beans production | Newly formed |
|  |  | SAIDIA | 2008/09 | NEW | 13 | 11 | 24 | Poultry production | Newly formed |
| NYABIYONZA | NYABIYONZA | UMOJA | 2008/09 | NEW | 8 | 3 | 11 | Maize production | Newly formed |
|  |  | TUMAINI | 2008/09 | NEW | 13 | 11 | 24 | Beans production | Newly formed |
|  |  | SAIDIANA | 2008/09 | NEW | 7 | 9 | 16 | Maize production | Newly formed |
|  |  | UMOJA NI NGUVU | 2008/09 | NEW | 8 | 3 | 11 | Beans production | Newly formed |
|  | BUKANGARA | UPENDO | 2008/09 | NEW | 13 | 11 | 24 | Maize production | Newly formed |
|  |  | TWEJUNE | 2008/09 | NEW | 12 | 3 | 15 | Beans production | Newly formed |
|  |  | TWIMANYE | 2008/09 | NEW | 10 | 6 | 16 | Maize production | Newly formed |
|  |  | ENDELEZA | 2008/09 | NEW | 11 | 19 | 30 | Beans production | Newly formed |
| NYAKAKIKA | NYAKAKIKA | MILENIUM | 2008/09 | NEW | 16 | 9 | 25 | Beans production | Newly formed |
|  |  | BUANGA | 2008/09 | NEW | 16 | 9 | 25 | Poultry production | Newly formed |
|  |  | KOMESHA | 2008/09 | NEW | 14 | 11 | 25 | Beans production | Newly formed |
|  |  | TAJIRIKA | 2008/09 | NEW | 14 | 11 | 25 | Poultry production | Newly formed |
|  | KAYUNGU | TUELIMISHE | 2008/09 | NEW | 13 | 12 | 25 | Beans production | Newly formed |
|  |  | TWENDENI | 2008/09 | NEW | 8 | 3 | 11 | Banana Production | Newly formed |
|  |  | MAENDELEO | 2008/09 | NEW | 8 | 3 | 11 | Banana Production | Newly formed |
|  |  | CHAPAKA KAZI | 2008/09 | NEW | 13 | 11 | 24 | Maize Production | Newly formed |
| KIBINGO | KIBINGO | TUJIAJIRI | 2008/09 | NEW | 7 | 9 | 16 | Maize Production | Newly formed |
|  |  | UKAKAMAVU | 2008/09 | NEW | 8 | 3 | 11 | Maize production | Newly formed |
|  |  | MWANZO MGUMU | 2008/09 | NEW | 13 | 11 | 24 | Maize production | Newly formed |
|  |  | UMOJA | 2008/09 | NEW | 12 | 3 | 15 | Maize production | Newly formed |
|  | KIHINDA | AMANI | 2008/09 | NEW | 16 | 9 | 25 | Maize production | Newly formed |
|  |  | FAGILIA | 2008/09 | NEW | 16 | 9 | 25 | Maize production | Newly formed |
|  |  | UMOJA | 2008/09 | NEW | 13 | 4 | 17 | Maize production | Newly formed |
|  |  | MWANGAZA | 2008/09 | NEW | 19 | 11 | 30 | Maize production | Newly formed |
| KIRURUMA | NYAKAGOYAGOYE | MAENDELEO | 2008/09 | NEW | 15 | 9 | 24 | Maize production | Newly formed |
|  |  | MAPAMBANO | 2008/09 | NEW | 16 | 13 | 29 | Maize production | Newly formed |
|  |  | MUUNGANO | 2008/09 | NEW | 7 | 9 | 16 | Poultry production | Newly formed |
|  |  | JITIHADA | 2008/09 | NEW | 8 | 3 | 11 | Poultry production | Newly formed |
| BUGENE | BUJURUGA | FARIJIKA | 2008/09 | NEW | 14 | 11 | 25 | Bees keeping | Newly formed |
|  |  | TUSAIDIANE | 2008/09 | NEW | 14 | 11 | 25 | Piggery production | Newly formed |
|  |  | KUJIAJIRI | 2008/09 | NEW | 13 | 12 | 25 | Maize production | Newly formed |
| WARD | VILLAGE | NAME OF PFG | YEAR | NUMBER OF MEMBERS | ENTERPRISE | REMARKS |
|  |  |  | FORMED | GRADUATED | Male | Female | Total |  |  |
|  |  | UMOJA NI NGUVU | 2008/09 | NEW | 10 | 15 | 25 | Maize production | Newly formed |
|  | LUKALE | TWEKAZE | 2008/09 | NEW | 0 | 23 | 23 | Bean Production | Newly formed |
|  |  | AZIMIO | 2008/09 | NEW | 10 | 10 | 20 | Maize Production | Newly formed |
|  |  | TEGEMEO | 2008/09 | NEW | 15 | 10 | 25 | Horticultural Crops | Newly formed |
|  |  | TUJIKOMBOE | 2008/09 | NEW | 10 | 6 | 16 | Banana Wine | Newly formed |
| NDAMA | NYABWEGIRA | MABORESHO | 2008/09 | NEW | 11 | 19 | 30 | Banana Production | Newly formed |
|  |  | TUKOMBOANE | 2008/09 | NEW | 18 | 9 | 27 | Banana Production | Newly formed |
|  |  | DUNDULIZA | 2008/09 | NEW | 14 | 11 | 25 | Maize Production | Newly formed |
|  |  | SHIRIKIANA | 2008/09 | NEW | 8 | 3 | 11 | Maize Production | Newly formed |
| NYAKAHANGA | OMURUSIMBI | KAZIKAZI | 2008/09 | NEW | 13 | 11 | 24 | Banana Production | Newly formed |
|  |  | CHANGAMUKA | 2008/09 | NEW | 13 | 12 | 25 | Banana Production | Newly formed |
|  |  | TWENDE KAZI | 2008/09 | NEW | 9 | 16 | 25 | Maize Production | Newly formed |
|  |  | SHIRIKIANA | 2008/09 | NEW | 14 | 11 | 25 | Maize Production | Newly formed |
| NYAKASIMBI | BUJARA | OMURUBALE | 2008/09 | NEW | 10 | 13 | 23 | Beans production | Newly formed |
|  |  | CHAIBUMBA | 2008/09 | NEW | 10 | 15 | 25 | Maize production | Newly formed |
|  |  | TWEJUNE | 2008/09 | NEW | 7 | 17 | 24 | Beans production | Newly formed |
|  |  | KAINA | 2008/09 | NEW | 9 | 16 | 25 | Maize production | Newly formed |
| BUGOMORA | NYAMIYAGA | FANIKISHA | 2008/09 | NEW | 14 | 11 | 25 | Poultry Production | Newly formed |
|  |  | MAENDELEO | 2008/09 | NEW | 8 | 3 | 11 | Banana production | Newly formed |
|  |  | UMOJA | 2008/09 | NEW | 13 | 11 | 24 | Beans Production | Newly formed |
|  |  | IMARISHA | 2008/09 | NEW | 14 | 11 | 25 | Maize production | Newly formed |
| TOTAL 20 | 30 | 120 |  |  | 1447 | 1134 | 2577 |  |  |

# DISTRICT AGRICULTURAL SECTOR INVESTMENT PROJECT (DASIP)

# FINANCIAL STATUS OF NEWLY FORMED PARTICIPATORY FARMER GROUPS (PFGs)

NAME OF DISTRICT: KARAGWE						QUARTER; SECOND

REPORTING DATE: 2 Jan 2009						YEAR: 2008/09

# NAME OF REPORTING OFFICER: SAMUEL STAMBULI

# Annex 4

| Village | Number of PFG Members | Type of Enterprise | Total Cost (Tsh. ‘000) | Group Contribution (Tsh. ‘000) | Contribution from DASIP (Tsh. ‘000) | Balance (Tsh. ‘000) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Total | Disbursed | Balance | Unallocated |  |
|  | Male | Female | Total |  |  |  |  |  |  |  |  |
| KYERERE | 15 | 11 | 26 | Improved Banana production | 938 | 438 | 500 | 0 | 500 | 0 | 0 |
|  | 14 | 10 | 24 | Improved poultry production | 938 | 438 | 500 | 0 | 500 | 0 | 0 |
|  | 16 | 9 | 25 | Improved poultry production | 938 | 438 | 500 | 0 | 500 | 0 | 0 |
|  | 19 | 11 | 30 | Improved poultry production | 938 | 438 | 500 | 0 | 500 | 0 | 0 |
| KITWE | 14 | 11 | 25 | Improved Onion production | 1090 | 590 | 500 | 0 | 500 | 0 | 0 |
|  | 16 | 13 | 29 | Improved Onion production | 1402 | 902 | 500 | 0 | 500 | 0 | 0 |
|  | 15 | 9 | 24 | Improved banana production | 1208 | 708 | 500 | 0 | 500 | 0 | 0 |
|  | 23 | 2 | 25 | Improved poultry production | 900 | 400 | 500 | 0 | 500 | 0 | 0 |
| KIBIMBA | 17 | 8 | 25 | Improved maize production | 900 | 400 | 500 | 0 | 500 | 0 | 0 |
|  | 10 | 15 | 25 | Improved Banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 18 | 9 | 27 | Improved poultry production | 780 | 280 | 500 | 0 | 500 | 0 | 0 |
|  | 14 | 11 | 25 | Improved poultry production | 780 | 280 | 500 | 0 | 500 | 0 | 0 |
| BUSINDE | 16 | 8 | 24 | Improved banana production | 1300 | 800 | 500 | 0 | 500 | 0 | 0 |
|  | 15 | 7 | 22 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 17 | 9 | 26 | Improved poultry production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 11 | 14 | 25 | Improved beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| ITEERA | 16 | 10 | 26 | Improved Banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 18 | 9 | 27 | Improved maize production | 1300 | 800 | 500 | 0 | 500 | 0 | 0 |
|  | 10 | 14 | 24 | Improved beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 14 | 13 | 27 | Improved maize production | 1300 | 800 | 500 | 0 | 500 | 0 | 0 |
| RWABWERE | 16 | 9 | 25 | Improved Banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 18 | 7 | 25 | Improved Banana production | 950 | 450 | 500 | 0 | 500 | 0 | 0 |
|  | 18 | 9 | 27 | Improved Tomato production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 13 | 14 | 27 | Improved Tomato production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| KIHANGA | 15 | 6 | 21 | Improved coffee production | 1100 | 600 | 500 | 0 | 500 | 0 | 0 |
|  | 14 | 15 | 29 | Improved Banana production | 900 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 7 | 9 | 16 | Improved coffee production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 15 | 10 | 25 | Improved Poultry production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| KATERA | 8 | 3 | 11 | Improved Banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 13 | 11 | 24 | Improved Tomato production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 12 | 3 | 15 | Improved Goat production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 0 | 18 | 25 | Improved poultry production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| KIBONA | 14 | 7 | 21 | Improved poultry production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 18 | 9 | 27 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 5 | 7 | 12 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 10 | 5 | 15 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| IGURWA | 15 | 10 | 25 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 18 | 8 | 26 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 11 | 15 | 26 | Improved Banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 17 | 7 | 24 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| MASHESHE | 14 | 15 | 29 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 17 | 9 | 26 | Improved coffee production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 12 | 13 | 25 | Improved poultry production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 12 | 14 | 26 | Improved Banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| NYAMIYAGA | 14 | 11 | 25 | Improved poultry production | 1100 | 600 | 500 | 0 | 500 | 0 | 0 |
|  | 8 | 3 | 11 | Improved Banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 14 | 11 | 25 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 13 | 11 | 24 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| BUJARA | 10 | 13 | 23 | Improved beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 10 | 15 | 25 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 7 | 17 | 24 | Improved beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 9 | 16 | 25 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| OMURUSIMBI | 13 | 11 | 24 | Improved Banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 13 | 12 | 25 | Improved Banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 9 | 16 | 25 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 14 | 11 | 25 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| NYABWEGIRA | 11 | 19 | 30 | Improved Banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 18 | 9 | 27 | Improved Banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 14 | 11 | 25 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 8 | 3 | 11 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| LUKALE | 0 | 23 | 23 | Improved Beans production | 670 | 170 | 500 | 0 | 500 | 0 | 0 |
|  | 10 | 10 | 20 | Improved maize production | 640 | 140 | 500 | 0 | 500 | 0 | 0 |
|  | 15 | 10 | 25 | Improved Onion production | 775 | 275 | 500 | 0 | 500 | 0 | 0 |
|  | 10 | 6 | 16 | Banana wine | 829.5 | 329.5 | 500 | 0 | 500 | 0 | 0 |
| NYAKAYANJA | 26 | 12 | 38 | Vegetable production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 4 | 16 | 20 | Maize Production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 13 | 12 | 25 | Improved poultry production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 10 | 8 | 18 | Vegetable production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| KAYANGA | 4 | 14 | 18 | Improved Maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 16 | 9 | 25 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 14 | 12 | 26 | Improved poultry production | 900 | 400 | 500 | 0 | 500 | 0 | 0 |
|  | 18 | 9 | 25 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| CHAMCHUZI | 7 | 16 | 13 | Improved Maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 8 | 3 | 11 | Improved Beans production | 1200 | 700 | 500 | 0 | 500 | 0 | 0 |
|  | 13 | 11 | 24 | Improved Maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 12 | 3 | 15 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| KAKURAIJO | 0 | 15 | 15 | Improved Tree Nursery | 750 | 250 | 500 | 0 | 500 | 0 | 0 |
|  | 14 | 10 | 24 | Improved Poultry production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 19 | 11 | 30 | Improved Poultry production | 753 | 253 | 500 | 0 | 500 | 0 | 0 |
|  | 15 | 9 | 14 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| KIBONDO | 16 | 13 | 29 | Improved banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 7 | 9 | 16 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 8 | 3 | 11 | Improved banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 12 | 14 | 26 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| IHEMBE II | 8 | 3 | 11 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 13 | 11 | 24 | Improved poultry production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 12 | 3 | 15 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 13 | 11 | 24 | Improved poultry production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| NYABIYONZA | 8 | 3 | 11 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 13 | 11 | 24 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 7 | 9 | 16 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 8 | 3 | 11 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| BUKANGARA | 13 | 11 | 24 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 12 | 11 | 23 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 10 | 24 | 24 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 15 | 10 | 25 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| NYAKAKIKA | 16 | 9 | 25 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 17 | 9 | 26 | Improved poultry production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 20 | 10 | 30 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 13 | 13 | 26 | Improved pig production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| KAYUNGU | 13 | 12 | 25 | Improved banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 8 | 15 | 23 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 10 | 11 | 21 | Improved banana production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 13 | 11 | 24 | Improved Beans production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| KIBINGO | 13 | 12 | 25 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 14 | 11 | 25 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 12 | 14 | 26 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 8 | 15 | 23 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| KIHINDA | 16 | 9 | 25 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 16 | 9 | 25 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 13 | 4 |  | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 13 | 17 | 30 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| NYAKAGOYAGOYE | 15 | 9 | 24 | Improved poultry production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 16 | 13 | 29 | Improved poultry production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 7 | 9 | 15 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 15 | 10 | 25 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
| BUJURUGA | 14 | 11 | 25 | Improved bees keeping | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 16 | 9 | 25 | Improved piggery production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 13 | 12 | 25 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 10 | 15 | 25 | Improved maize production | 1000 | 500 | 500 | 0 | 500 | 0 | 0 |
|  | 1529 | 1262 | 223 |  | 122,527.5 | 179,653 | 60,000 |  | 60,000 |  |  |