KIBONDO DISTRICT COUNCIL

| District Executive Director Office, P.o Box 43, KIBONDO. Tel. 028-2820084 Fax. 028-2820473 Ref. P/DASIP/VOL.III/18 |  | Agricultural Department, P.o Box 9, KIBONDO. Tel. 028-2820287 |
| --- | --- | --- |

District Agricultural Sector Investment Project (DASIP)

SEMI-ANNUAL REPORT

JULY – DECEMBER, 2008/2009

# List of abbreviations

DASIP	District Agriculture Sector Investment Project

FFS		Farmer Field School

PFG		Participatory Farmer Group

FP		Farmer Practice

VADP		Village agriculture development Plans

PCU		Project Coordinating Unity

FCB               Farmers Capacity Building

CP                 Community Planning

FF’s               Farmers  Facilitators

BOQ		Bill of Quantities

KIWOSA	Kibondo Women SACCOS

O & OD	Opportunity and Obstacle for Development

July – December DASIP progress report 2008/09 KIBONDO DISTRICT

# Introduction

This report gives the status of project implementation of the past six(6) months from July 2008 to December 2008. The report starts by listing the activities carried out in the period and goes on giving both physical and financial status of their respective implementation. It should be noted that activities done so far includes implementation of the carried over activities from the fourth quarter of financial year 2007/2008. The report also explains the performance of the FFS`s for the past cropping season by comparing yields under FP and IPPM and all the important information from FFS`s. The component of monitoring and evaluation/verification of the planned activities were carried out in all DASIP target villages in the district. At the end, the report cites problems encountered during the period.

These quarters verification of implementation of the past and activities plans for the financial year 2008/2009 was conducted under field appraisal, which was carried by PCU staff in collaboration with district DASIP staff and the beneficiaries.

# 2.0 Plan and implementation status

2.1	Farmers capacity building

- Senstization and formation of six more PFG’s for each village under DASIP.

135 PFG’s out of 180 target in 2008/ 2009 have been formed.

- Trainig of farmer facilitators.

28 FF’s out of 30 targeted have received train on the major principles of crops and livestock production.

- Distribution of agricultural inputs/training materials to villages under DASIP.

135 PFG’s formed 2008/2009 have been supplied

2.2      Community planning and investment

Table 1. Community investments 2006/2007/2008:

|  | FUNDS ISSUED 2006/2007/2008Tsh. (000 ) |  |
| --- | --- | --- |
| WARD | VILLAGE | PROJECT NAME | BENEF. | DASIP | TOTAL | IMPLEMENTATION STATUS | REMARKS |
| Kibondo | Kibondo | Rehabilitation of rural feeder road. | 2,400 | 9,600 | 12,000 | Completed |  |
| Kibondo | Kibondo | Rice mill & Flour packaging machine. | 5,000 | 5,000 | 10,000 | Co-funded and procurement process begin | Co-funded by KIWOSA and DASIP after the former Kabwigwa Women Association failed to do so. |
| Misezero | Twabagondozi | Construction of 4 box culverts for rural feeder road | 2,400 | 9,600 | 12,000 | Completed |  |
| Misezero | Twabagondozi | Construction of rural feeder road | 1,600 | 6,400 | 8,000 | BOQ prepared | Due to delayed opening Bank A/C |
| Misezero | Twabagondozi | Construction of Cattle dip | 3,000 | 12,000 | 15,000 | At initial stage of implementation(Construction) | Due to delayed opening Bank A/C |
| Busagara | Kasaka | Rehabilitation of a Cattle dip | 1,340 | 5,360 | 6,700 | Completed |  |
| Muhange | Muhange | Coffee pulpier machine-MUCUPA | 5,000 | 5,000 | 10,000 | Co-funded and it is at procurement stage | Due to delayed opening Bank A/C |
| Kasanda | Kasanda | Rehabilitation of rural feeder road | 1,200 | 4,800 | 6,000 | BOQ prepared and it is at tender stage | Due to delayed opening Bank A/C |
| Kasanda | Kasanda | Construction of Cattle dip | 3,000 | 12,000 | 15,000 | Construction is at 80% of implementation | Due to delayed opening Bank A/C |
| Kasuga | Kinonko | Rehabilitation of rural feeder road at Katengera Irrigation scheme | 800 | 3,200 | 4,000 | Tender processing | Due to delayed opening Bank A/C |
| Rugongwe | Kichananga | Rehabilitation of rural feeder road | 5,800 | 23,200 | 29,000 | Tender processing | Due to delayed opening Bank A/C |
| Nyabibuye | Nyabibuye | Construction of a Slaughter slab | 800 | 3,200 | 4,000 | Completed |  |
| Gwanumpu | Bukirilo | Construction of a Slaughter slab | 800 | 3,200 | 4,000 | Tender processing | Due to delayed opening Bank A/C |
|  |  |  | 33,140 | 102,560 | 135,700 |  |  |

Table 2. Community investments 2008/2009:

|  | WARD | VILLAGE | NAME OF PROJECT | BEN.CONTR. TSHS.`000’ | DASIP FUNDS TSHS.`000’ | TOTAL TSHS.`000” | IMPLEMENTATION STATUS | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Kibondo | Kibondo | Rural feeder road | 3,680 | 14,720 | 18,400 | Transfer of money to respective project a/c | Compliance delay of VADP action plan to district head quarter |
| 2 | Gwanumpu | Bukirilo | Rural feeder road | 5,000 | 20,000 | 25,000 | Transfer of money to respective project a/c | Compliance delay of VADP action plan to district |
| 3 | Itaba | Kigogo | Crop storage facility | 6,900 | 27,600 | 34,500 | Transfer of money to respective project a/c | Compliance delay of VADP action plan to district |
| 4 | Kakonko | Kanyonza | Rural feeder road | 5,600 | 22,400 | 28,000 | Transfer of money to respective project a/c | Compliance delay of VADP action plan to district |
| 5 | Kakonko | Kabingo | Rural feeder road | 5,020 | 20,080 | 25,100 | At BOQ stage | Compliance delay of VADP action plan to district |
| 6 | Kakonko | Itumbiko | Rural feeder road | 3,000 | 12,000 | 15,000 | At BOQ stage | Compliance delay of VADP action plan to district |
| 7 | Nyamtukuza | Churazo | Crop storage facility | 6,900 | 27,600 | 34,500 | Transfer of money to respective project a/c | Compliance delay of VADP action plan to district |
|  | TOTAL |  | 36,100 | 144,400 | 180,500 |  |  |

# 3.0 Training of DASIP stakeholders

There was no any training conducted to DASIP staff on first quarter. However, the Project Officers, the District Agriculture and livestock Development Officers, The District Planning Officers and the District Executive Directors from all 28 districts implementing DASIP had a workshop in Mwanza. The objective of the workshop was to review the performance of DASIP in the project area for the past two years. They reviewed the performance and find solution to those problems which seemed to be common in the project area in hindering effective implementation of the project. At the end strategies to improve and fasten the speed of implementation were put.

On the second quarter training of farmers facilitators were conducted, 28 FF’s from 28 villages under DASIP project were involved.

# 4.0 Supervision

Supervision activities carried were to monitor and to verify the implementation of the above-mentioned projects. Project beneficiaries were advised open bank accounts, forming six more PFG`s and their respective selected farming enterprises for each village under the DASIP project, handing over of their business/project plans attached with the minutes to the DASIP district head quarter for further action before disbursement this project financial year. The Training Project Coordinator from PCU recommended on these during his visit in the district at the end of this first quarter.

### 5.0 Out put results so far achieved

### 5.1 Farmers capacity building

- Farmers have shown greater interest in farmers’ field school, extension methodology. They have recognized that, training through FFS have more impact than the previous approach. Learning by doing sticks more, and is easier to practice the skills to their field. The Umoja PFG of Kichananga village under FFS succeeded to produce and yield 336 Kgs of groundnuts alongside the 180 Kgs under prior farmers practices. Tumaini PFG of Kigogo village under FFS also succeeded to produce and yield 15 bags of maize grains alongside the 3 bags under prior farmers practices. Maendeleo PFG of Mugunzu village under FFS also succeeded to produce and yield 14 bags of maize grains alongside the 3 bags under prior farmers practices.

5.2 Community planning investment

- Completion of Rehabilitation of rural feeder road at Kibondo village. There after, accessibility to and from Twabagondozi-Kilalangona have been made easier to be accessible throughout a year by project beneficiaries and other stakeholders in agricultural sector.

- Construction of box culverts for rural feeder road also completed. This has made the feeder road free from been damaged by randomly running water across the feeder road.

5.3 Lesson learned and experience gained

- Village leaders show more commitment in project activities if facilitated (trained in project management as well as monitoring and evaluation).

- Farmers have appreciated FFS methodology as a means of disseminating knowledge to them. They said it is an enjoyable, funny methodology especially when  referring to AESA

### 6.0 Project to date

6.1	Farmers capacity building

- The total of 43 PFG’s formed last financial year (2007/2008) having a total of 978 farmers of which 568 be males and 410 be females have been trained on the major principles of some different crops through FFS’s accordingly.

- PFG’s in each village under the DASIP project for 2008/2009 financial year have been done, so far 135 out 180 FPG’s targeted have been formed.

- 28 FF’s out of 30 have been trained on the major principles of crop and livestock production.

  - Community planning and investments

- Among 13 micro projects for 2006/2007/2008, 4 have been completed and 9 at different levels of implementation not yet completed as described on table 1 above.

- In this 2008/2009 financial year, 7 village micro projects under DASIP have been planed and financed as shown in table 2 above.

Below is a success story from Kibondo village, regarding the Rehabilitated Farm access road about 10 Km.

Kibondo village is among the four villages of Kibondo ward. The village is important for various economic activities such as Food crops production. Most of these activities to the large extent are carried out faraway distance (North-east) from the Village head quarter. According to Mzee Hamisi Omari who is a resident of Kibondo village and is among farmers working at Kilalangona area, said that “Before rehabilitation of the farm access road in the village, accessibility to and from the production area was difficult due to water logging along the way especially during rainy season which made transportation cost of the agricultural produce to be relatively high because initially it was not possible to hire a motor car to carry the products and instead the product was been carried by using human power, which generally was expensive and also too laborious compared to nowadays where the products are easily carried by motor cars”. He continued to explain that “Time spent to reach to the farm has been reduced since the road has made a short cut resulting into increased working time and hence working area and production. After completion of feeder road, accessibility to and from the field has became easier and throughout the year. We give much thanks to the project, donor and Tanzania government as a whole”. Mzee Hamisi Omari ended that.

7.0 Financial status of budget and disbursement 2008/2009

In these 1st two quarters the money transferred into Kibondo DASIP account  was meant for, as described in the table below:-

Table 3:  Summary of disbursement and expenditure of funds

| SN | Amount disbursed | Activity | Expenditure | Balance | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1. | 24,000,000.00 | Mini -projects of participatory farmer groups | 11,200,000.00 | 12,800,000.00 | Delay in opening bank a/c- Activity is going on |
| 2. | 90,000,000.00 | Season long Training of PFG’s | 5,602,400.00 | 84,397,600.00 | Activity is going on |
| 3. | 2,300,000.00 | PFG’s formation for 2008/2009 | 2,300,000.00 | Nil |  |
| 4. | 1,800,000.00 | Motorcycle allowances | 1,800,000.00 | Nil |  |
| 5. | 1,350,000.00 | Office operation & maintenance costs-FCB&CP | 640,000.00 | 710,000.00 | On going activity |
| 6. | 5,025,000.00 | District Staff field allowances | 280,000.00 | 4,745,000.00 | On going activity |
| 7. | 144,400,000.00 | Village Micro Project implementation | 144,400,000.00 | Nil |  |
| 8. | 10,042,000.00 | Training Farmer Facilitators(FF’s) | 5,102,000.00 | 4,940,000.00 | Activity is going on |
| Total | 278,917,000.00 |  | 171,324,400.00 | 107,592,600.00 |  |

Source: Disbursement record and expenditure report 2008/2009

8.0 Problems and Challenges

The following are the challenges/problems so far encountered.

- Most farmers have low purchasing power the fact that makes them unable to budgets for their farms in the aspect of farm inputs. This made most farmers fail to apply what they learned from FFS in 2007/2008 cropping season. However, they have taken this as a challenge and promised to budget for the farm inputs ready to practice the skill they acquired in FFS in this 2008/2009 cropping season.

- Transport for execution of project activities is still a problem despite the fact that project staffs have been provided with motorcycles. When there is a need  to travel as a team the vehicle is highly needed, since we some time need to work as a team with other staffs like, engineers, community development staffs, cooperative officers etc.

- The procurement procedures take so long time, the fact that leads/contributes to delayed implementation of planned activities.

- Most farmers have low income in such that can not afford to organize themselves and ask for 50% Co-funding Micro projects as a DASIP precondition.

- Inflation has interfered with DASIP budgets- rapid raise of farming inputs e.g. Pesticides/ insecticides, fertilizers and building/ construction materials e.g. Cements.

# 9.0 Way Forward

- To emphasize training and community sensitization so that they can contribute where required and implement their activity planned.

- To facilitate capacity building training to all stakeholders for project sustainability.

- To base on contract, efficiency and time specific to complete implementation of planned activities for 2007/2008 and 2008/2009 financial years.

- To carry on monitoring and evaluation of project activities.

# 10.0 Recommendation

  - We recommend the money provided as motorcycle maintenance and fuel allowance to be increased from the current seventy five thousand per month to one hundred fifty thousand due to the fact that, the cost of maintenance as well as the price of fuel increases. The fund allocated as field allowance for staff doubled the current amount. This is because the execution of DASIP activities needs multi-disciplinary technocrats (i.e. engineers, technicians, cooperative officers, etc.) of which the current budget cannot suffice.

  - Since that most of the farming enterprises especially crop productions are seasonal, timely need and rain fed, if possible procurement procedures for DASIP activities implementation to be revised by PCU.

  - The 50% Co-funding precondition to be revised at least to be 20%.

# 11.0 Conclusion

Provision of vehicles to the districts under DASIP, reviewing of some preconditions and procurement procedures may increase the adoption   and efficiency rates of Implementation of DASIP activities plans. The district has planned to do much better on implementation and supervision of the ongoing village micro projects for the past as well as this financial year. On top of that, monitoring and evaluation for the project activities need to be of paramount importance to charter for efficiency, effective, economical and timely implementation of the planned activities.

# Text boxes

Kibondo – Kilalangona road after completion of rehabilitation. .

Farm products are nowadays easily carried by motorcars