TABLE OF CONTENTS								 page

1.0 Introduction and background information…………………………...		4

2.0 Project Implementation status…………………………………………...		5

2.1 Physical Status……………………………………………………………....		5

2.1.1 Farmers Capacity Building Component……………………………..		5

2.1.2 Community planning and Investment in Agriculture……………...		5

3.0 Implementation Status………………………………………………….....		6

3.1 Farmer Capacity Building Component………………………………...		6

3.2 Community Planning and Investment in Agriculture………………..		7

3.2.1 Carried Over Activities FY 20007/08…………………………………..		7

3.2.2 Implementation Status for planned second quarter activities

FY2008/09…………………………………………………………………………		7

3.3 Support to Rural Financial Services and Marketing………………….		8

4.0 Financial Status……………………………………………………………...		9

4.1 Funds received……………………………………………………………...		9

4.2 Funds spent…………………………………………………………………..		10

5.0 Problems and Challenges…………………………………………………	11

6.0   Outputs, achievements and results…………………………………….	13

7.0   Plans of implementation in the third quarter (January-march 2009).................13.

8.0. List of Annexes	…………………………………………………………………….14

Annex I 	PFGs 2007/2008, Farm budgets for FFS (With and

Without FFS), and Financial Status of PFGs......

Annex II 	Success story...........................................................................

Annex III    Table matrix shown participatory farmer groups formed FY 2008/09

……………………………………………………………………

Annex IV     Funds transferred to PFGs formed FY 2007/08 & PFGs FY

2008/09……………………………………………….

Annex V 	Pictures of completed structures (cattle dip tanks,

slaughter slab, market shed and household cereal

storage facility)...............................................................

Abbreviations and Acronyms

BOQ	-	         Bill of Quantities

DASIP	 -               District Agriculture Sector Investment 			         Project

DE		-		District Engineer

DED		-		District Executive Director

DTCs         -		District Training Coordinators

FFS		-		Farmer Field Schools

FFs           -                Farmer facilitators

FY 		-	 	Financial Year

MDC	-		Maswa District Council

PCU		-		Project Co-ordination Unit

PFGs	-               Participatory Farmer Groups

VEO		-		Village Executive Officers

WEO	-		Ward Executive Officer

- INTRODUCTION AND BACK GROUND INFORMATION

Maswa District Council (MDC) is among 28 district councils funded by the District Agriculture Sector Investment Project (DASIP). The objective of the project is mainly crop productivity and income enhancement to rural farming community. The Project covers 30 villages in 18 wards in the district.

At the district level the project has three main components namely:-

- Farmer’s capacity building component

- Community planning and investment in Agriculture component.

- Support to Rural Financial Services and Agriculture Marketing component.

This report briefly explains progress of implementing DASIP activities component-wise from July to December 2008 of FY 2008/2009. The report starts by outlining the plan of implementation and proceeds to explain physical and financial performance, along with problems and challenges met during the course of implementation. The report winds up by outlining some of the measures/suggestions taken to intervene problems and pointing out plans of implementation in the third quarter (January-March 2009).

It should be noted that activities done so far were implementation of the carried over activities from the FY 2007/08. This includes construction of two cattle dip tanks at Mwabomba and Mwabagalu villages, Rehabilitation of cattle dip tanks at Isanga, Mwakidiga, Kinamwigulu and Mwamihanza villages, construction of market shed and slaughter slab at Jija village and construction of house hold burnt brick storage facilities, construction of charco dams at Mwabaraturu and Bushitala villages, Rehabilitation of charco dams at Nyabubinza, Kidema and Mwamihanza villages. Also during the period under report farmer capacity building activities like formation of PFGs, training of farmer facilitators and facilitation of PFGs to open bank accounts were executed.

- PROJECT IMPLEMENTATION STATUS

  - Physical status

    - Farmers Capacity building component.

Under this component, major activities planned were:-

- Data collection and analysis of  established FFS

- Formation of 180 PFGs.

- Facilitation of 240  PFGs  in opening bank accounts for implementation of  FFS and economic mini-projects.

- Training of farmer facilitators (FFs)

- Establishment of FFS

- To conduct season long training of 180 PFGs

- Procurement of 80 pieces of bicycles

- Monitoring and supervision of FFS.

    - Community planning and Investment in Agriculture

The plan during the period under review was to finalize implementation of carried over activities FY2007/08 and planned activities FY 2008/09. Carried over activities include:-

- Construction/Rehabilitation of cattle dip tanks (5)

- Support 25 farmer groups with house hold burnt brick cereals  storage facilities (75)

- Construction/rehabilitation of charco dams (5)

- Construction of market shed and slaughter slab

Planned activities for the second quarter FY 2008/09 were:-

- To conduct topographic survey and designing of Kinamwigulu irrigation schemes.

- To construct 20 burnt bricks house hold storage facilities at four (4) villages.

- To construct one (1) cattle dip tank at Mwandete village and rehabilitation of one (1) cattle dip tank at Nyashimba village.

- To construct one (1) charco dam at Iyogelo village.

- To construct one (1) cotton storage   structure at Buhungukila village.

- To procure 20 pcs of oxen- weeders for Mwabagalu village.

- Procurement of 7 pieces of grain/ground nut/sweet potato milling/hulling machines for Mandela, Igunya, Isanga, Mwabayanda (M) and Senani villages.

- Construction of 6 shallow wells for Mandela, Mwabagalu, Mwabayanda(S), Mwabayanda (M), and Senani villages.

- Monitoring and supervision of village/group micro projects.

- IMPLEMENTATION STATUS FOR ACTIVITIES UNDER FARMER CAPACITY

BUILDING AND COMMUNITY PLANNING AND INVESTMENT IN AGRICULTURE COMPONENTS:-

  - Farmer capacity building component implementation status.

Data collection of all established FFS were collected. Analysis of Some selected FFS in terms of cost benefit was also done. The result of analysis indicates that cost benefit ratio is high in FFS than in farmer practice. The selected FFS with respect to PFGs names is presented as annex I a –I f. Either success story of Improving cotton storage and Increasing Crop quality at Mandela village is presented as annex II.

- 163 out of 180 target Participatory Farmer Groups have been formed where by 1499 are male members and 1240 are female members. Formation of the remaining 17 farmer groups are in progress. A table matrix showing formed group FY2008/09 is attached as annex III

- 152 formed Participatory Farmer Groups have been facilitated to open bank accounts ready for implementation of FFS. Facilitation of the remaining 48 PFGs are also in progress.

- 51 graduated Participatory Farmer Groups in last year (FY 2007/08) have been facilitated to open bank accounts for implementing economic mini-projects. names of  PFGs with their respective account numbers  & PFGs for FY 2008/09 in which funds have been transferred  is presented as an annex IV

- 30 farmer’s facilitators have been trained on improved technologies on crop and livestock production and management of farmer field school plots.

- The process of establishing FFS and seasonal long training are at initial stage.

- 80 pieces of bicycles have been procured.

  - .	Community planning and Investment in Agriculture

implementation status

    - Carried over activities FY 2007/08

- Improvement of Livestock infrastructures.

Under the improvement of livestock infrastructures achievements made so far includes:- Construction of two cattle dips at Mwabagalu and Mwabomba villages have been completed and in use. Two cattle dip tanks at Isanga and Mwamihanza have been rehabilitated. Kinamwigulu and Mwakidiga cattle dip tanks are under rehabilitation following tender award in this month (December).  Rehabilitation of charco dams at Nyabubinza and Kidema villages are in progress. Also one slaughter slab at Jija village has been completed. Either construction of charco dam at Mwabaraturu village is in progress (50% completion). Photos of the completed structures are attached as Annex V a -c.

- Improvement of market infrastructures

Under this activity, one market shed at Jija has been completed and its photo is presented as annex V.

- Improvement of post harvest storage facilities in 27 villages

Under improvement of post harvest storage facilities the target was to construct 75 burnt brick house hold storage facilities each with capacity of storing 3 tons of cereals in 25 villages. Eighteen (18) storage facilities at Mwandete, Mwabayanda, Kidema, Mwabagalu, Mwabaraturu and Hinduki village have been constructed. The rest 11 villages are still finalizing mobilization of local building materials. Provided in this report as annex V is a photo of completed house hold storage facility at Mwandete village.

3.2.2 Implementation Status for planned second quarter activities

FY 2008/09

- Topographic survey and designing of Kinamwigulu irrigation scheme not yet done as this activity is going to be executed by contractor who will be appointed by DASIP-PCU.

- Construction 20 burnt bricks house hold storage facilities in four (4) villages not yet done as the targeted community are still mobilizing local building materials together with opening project bank account.

- Construction of one (1) cattle dip tank at Mwandete village and rehabilitation of one (1) cattle dip tank at Nyashimba village not yet done as the targeted community are still mobilizing local building materials together with opening project bank account.

- Construction one (1) charco dam at Iyogelo village not yet done since the approved budget not yet released.

- Construction one (1) cotton storage   structure at Buhungukila village not yet done as the targeted community is still mobilizing local building materials together with the process of opening project bank account.

- Procurement 20 pieces of ox-weeders for Mwabagalu village are in the final stage.

- Procurement of 7 pieces of grain/ground nut/sweet potato milling/hulling machines for Mandela, Igunya, Isanga, Mwabayanda (M) and Senani villages not yet implemented as targeted community is still mobilizing local building materials together with the process of opening project account.

.

- Construction of 6 shallow wells for Mandela, Mwabagalu, Mwabayanda(S), Mwabayanda (M), and Senani villages not yet started as the targeted community is still in the process of opening project bank account.

- Monitoring and supervision of village/group micro projects for both community and group micro projects have been monitored and supervised so as to ensure good quality work and in the required standards.

  - . Support to Rural Financial Services  and Marketing

Until to date no any activity done as the DASIP-PCU Mwanza she is still consulting the best way of performing this component

4.0.	FINANCIAL STATUS

# 4.1.	Funds Received

For the period of July to December 2008 for FY 2008/09 Maswa District Council has received Tshs 253,117,000/= plus Tshs 108,673,380.50 as carried over for FY 2007/08 funds from DASIP- PCU Mwanza as a total budget for the summarized activities in table no. 1 below.

# Table No 1: Funds received as at 31st December, 2008

| Date of letter for funds transfer | Amount (Tshs) | Targeted activities |
| --- | --- | --- |
| 08th/08/2008 | 8,175,000/= | District office operation and maintenance Motorcycle allowances Field staff allowances |
| 22nd /08/2008 | 24,000,000 | To support 60 graduated PFGs min-projects |
| 04/09/2008 | 2,300,000/= | Formation of Participatory Farmer groups (PFGs) |
| 09th/09/2008 | 90,000,000/= | Seasonal long training of PFGs |
| 11th/10/2008 | 118,600,000/= | Support 19 village micro projects |
| 6th/11/2008 | 10,042,000/= | Training of 30 Farmer Facilitators. |
| 1st /07/2008 | 108,673,380.50 | Carried over funds for FY 2007/08 |
| Total amount of funds as at 31st December 2008 | 361,790,380.50 |  |

# 4.2. 	Funds Spent As At 31st December, 2008

A total of 151,056,210/= was spent both for community planning and farmers capacity building components. The analysis of expenditure component wise is summarized in the table No. 2 below.

# Table No. 2 Expenditure funding statement component-wise as at 31/12/2008:

| COMPONENT | ACTIVITY | AMOUNT SPENT (July-Sept.2008) | CUMMULATIVE (July-Dec. 2008) | REMARKS |
| --- | --- | --- | --- | --- |
| Community planning and investment in agriculture component | Motorcycle operating costs | 300,000 | 600,000 | Allowances for 4 months |
|  | Staff field allowances | 4,678,000 | 8,888,000 |  |
|  | Bank charges | 15,000 | 90,000 |  |
|  | village micro projects | 56,849,144 | 56,849,144 | Transfer of funds (48,640,000/=) to 16 village/group micro projects are in progress |
|  | Office operation and maintenance | 763,200 | 1,187,200 |  |
| Farmer capacity building component | Motorcycle operating costs | 300,000 | 600,000 | Allowances for 4 months |
|  | Office operation and maintenance | 400,000 | 600,000 |  |
|  | Staff field allowances | 350,000 | 600,000 |  |
|  | Purchasing of 80 bicycles | 0 | 7,466,666 | Carried over activity |
|  | To support 60 PFGs min-projects | 0 | 17,400,000 |  |
|  | Formation of PFGs | 0 | 2,919,400 |  |
|  | Seasonal long training of PFGs | 0 | 45,000,000 |  |
|  | Printing of graduation certificates for PFGs members FY 2007/08 | 4,491,000 | 4,491,000 | Carried over activity |
|  | Purchasing of equipments for FFS FY2007/08 | 0 | 982,800 | Carried over activity |
|  | Bicycle allowances | 0 | 240,000 | Carried over activity |
|  | Training of 30 FFS in three phases | 0 | 3,142,000 | One phase training |
| TOTAL | 68,146,344 | 151,056,210 |  |

- PROBLEMS AND CHALLENGES (ISSUES AND CONSTRAINTS)

- Untimely release of funds delayed implementation to some of activities, for instance in this FY 2008/09 the planned first quarter activities which include construction works their funds released at the second week of October, 2008.

- Slow pace of community in mobilizing local building materials for construction activities for both community and group investment projects.

- Slow pace of project supervision communities and groups in opening bank project accounts for quick implementation of micro projects funded by DASIP, for instance out of 19 funded village/group micro projects only 11 to date have opened their micro project bank accounts.

- Low accountability and irresponsible of village local leaders

- Inadequate local artisans at village level to carry out construction of cereal burnt brick storage facilities.

- Untimely availability of technical staff such as District Engineer and Supplies officer causes slow pace in implementation of some micro project activities.

- Lack of clear guidelines on recurrent expenditures for village/group micro project supervision committees.

- The dominant culture of depending on the Government to do every thing for community/group micro projects impairs speed of implementation.

Table Na 3.	 List of challenges and actions taken / to be taken to address them.

| S / N | Issues | Action taken / to be taken | Responsible person |
| --- | --- | --- | --- |
| 1 | Slow response in opening micro project bank account. | To continue with sensitization of project supervision communities and groups to opening Bank project account for quick implementation of projects | DALDO DPO DMEO |
| 2 | Slow pace of community in mobilization of local building materials. | To continue educating community on the importance of implementing their projects within the planed time frame. To continue sensitize community on the importance of adhering to work plans and enforcement of village by Laws to laxity community members. | DPO DMEO VEO WEO |
| 3 | Low accountability and irresponsible village local leaders. | Enforcement of Local government ACT No. 7 of 1982 to non accountable and irresponsible local leaders. To continue with educating Local leaders on their responsibilities in implementing development projects. | DC DED |
| 4 | Untimely release of funds delayed implementation to some of activities | PCU-Mwanza to adhere to Annual Work Plan and Budget | PCU-Mwanza |
| 5 | Lack of clear guidelines on recurrent expenditures for village/group micro project supervision committees. | To prepare and submit to the respective districts guidelines on how recurrent expenditure can be accommodated in supervising village micro projects at committees’ level. | PCU-Mwanza |
| 6 | The dominant culture of depending on the Government to do every thing for community/group micro projects impairs speed of implementation. | Political and local leaders should continue educating the community that development is their own role and the government will support them only when they show their efforts. | DC Councilors Member of parliament |

- OUTPUTS,ACHIEVEMENTS AND RESULTS

The followings are the outputs/achievements/results obtained so far:-

- Capacity of ward and village staff as well as that of facilitation committees at ward level has been built.

- As pre-requisite for successful micro project implementation, team work has been established and is continued to be strengthened at district, ward and village levels.

- Awareness to micro project has been created and rise to the stakeholders, and enthusiasm to implement the micro projects has been raised.

- A total of 22 village/group micro projects have so far been completed

7.0 	 PLANS OF IMPLEMENTATION IN THE THIRD QUARTER (JANUARY-MARCH 2009).

- To continue with implementation of   Carried over activities (Charcodam and Cattle dips) and planned FY 2008/09 activities.

- Intensify monitoring and supervision so as to ensure good quality and timely completion of village/group micro projects.

- LIST OF ANNEXES

Annex I a. FARM BUDGET FOR FARMER FIELD SCHOOLS (WITH AND WITHOUT FFS) FOR TOMATO PRODUCTION FY 2007/08

NAME OF PFGs: NGUVU KAZI – MWABOMBA VILLAGE -MASWA DISTRICT COUNCIL

| REVENUE | UNIT | WITH FFS | WITHOUT FFS |
| --- | --- | --- | --- |
| Yield Post Harvest loss (10%) Net Yield Selling price Total Revenue | Kg./ Ha Kg./ Ha Kg./Ha Tshs/kg. Tshs/ Ha | 4070 407 3663 300/= 1,098,900/= | 1977.5 197.5 1780 300/= 534,000/= |
| Total cost | Tshs/Ha | 510,625/= | 368,125/= |
| Net Revenue | Tshs / Ha | 588.275/= | 174,000/= |
| Cost: Benefit Ratio |  | 1: 1. 1 | 1: 0. 5 |
| Increase in Yield | % | 105.8 | - |
| Break – Even price |  | 2.15 | 4.0 |

Source: M &E surveys, June 2008: Maswa District Council

I b. FARM BUDGET FOR FARMER FIELD SCHOOLS (WITH AND WITHOUT FFS) FOR   MAIZE PRODUCTION

NAME OF PFGs: WAKULIMA BORA B – TAMANU VILLAGE -MASWA DISTRICT COUNCIL

| REVENUE | UNIT | WITH FFS | WITHOUT FFS |
| --- | --- | --- | --- |
| Yield Post Harvest loss (5%) Net Yield Selling price Total Revenue | Kg./ Ha Kg./ Ha Kg./Ha Tshs/Kg. Tshs/ Ha | 2840 355 2485 300/= 745,500/= | 1950 243.75 1706.25 300/= 511,875/= |
| Total cost | Tshs/Ha | 425,000/= | 102,500/= |
| Net Revenue | Tshs / Ha | 320,500/= | 409,375/= |
| Cost: Benefit Ratio |  | 1: 0. 8 | 1: 4 |
| Increase in Yield | % | 45.6 | - |
| Break – Even price |  | 1.8 | 5.0 |

Source: M &E surveys, June 2008: Maswa District Council

I c. FARM BUDGET FOR FARMER FIELD SCHOOLS (WITH AND WITHOUT FFS) FOR GROUNDNUTS PRODUCTION

NAME OF PFGs: MSHIKAMANO – HINDUKI VILLAGE -MASWA DISTRICT COUNCIL

| REVENUE | UNIT | WITH FFS | WITHOUT FFS |
| --- | --- | --- | --- |
| Yield Post Harvest loss (12.5%) Net Yield Selling price Total Revenue | Kg./ Ha Kg./ Ha Kg./Ha Tshs/Kg. Tshs/ Ha | 1000 125 875 1500/= 1,312,500/= | 500 62.5 437.5 1500/= 656,250/= |
| Total cost | Tshs/Ha | 345,000/= | 127,500/= |
| Net Revenue | Tshs / Ha | 967,500/= | 528,750/= |
| Cost: Benefit Ratio |  | 1: 2. 8 | 1: 4 |
| Increase in Yield | % | 100 | - |
| Break – Even price |  | 3.8 | 5.1 |

Source: M &E surveys, June 2008: Maswa District Council

I d. FARM BUDGET FOR FARMER FIELD SCHOOLS (WITH AND WITHOUT FFS) FOR SUNFLOWER PRODUCTION

NAME OF PFGs: WALALASAGALA – SENANI VILLAGE -MASWA DISTRICT COUNCIL

| REVENUE | UNIT | WITH FFS | WITHOUT FFS |
| --- | --- | --- | --- |
| Yield Post Harvest loss (12.5%) Net Yield Selling price Total Revenue | Kg./ Ha Kg./ Ha Kg./Ha Tshs/kg. Tshs/ Ha | 667.5 83.4 584.1 3000/= 584,100/= | 125.5 19 133.5 3000/= 133,500/= |
| Total cost | Tshs/Ha | 338,750/= | 100,000/= |
| Net Revenue | Tshs / Ha | 245,350/= | 33,500/= |
| Cost: Benefit Ratio |  | 1: 0. 7 | 1: 0. 3 |
| Increase in Yield | % | 337.5 | - |
| Break – Even price |  | 5.2 | 4.0 |

Source: M &E surveys, June 2008: Maswa District Council

I e. FARM BUDGET FOR FARMER FIELD SCHOOLS (WITH AND WITHOUT FFS) FOR COTTON PRODUCTION

NAME OF PFGs: MAPINDUZI – BUSHITALA VILLAGE -MASWA DISTRICT COUNCIL

| REVENUE | UNIT | WITH FFS | WITHOUT FFS |
| --- | --- | --- | --- |
| Yield Post Harvest loss (5%) Net Yield Selling price Total Revenue | Kg./ Ha Kg./ Ha Kg./Ha Tshs/Ha Tshs/ Ha | 2405 120.25 2284.75 450/= 1,028,137.50/= | 460 23 437 450/= 196,650/= |
| Total cost | Tshs/Ha | 400,000/= | 135,000/= |
| Net cost Revenue | Tshs / Ha | 628,137.50/= | 61,650/= |
| Cost: Benefit Ratio |  | 1:1.6 | 1: 0.5 |
| Increase in Yield | % | 422.8 | - |
| Break – Even price |  | 2.6 | 1.1.5 |

Source: M &E surveys, June 2008: Maswa District Council

I f. FARM BUDGET FOR FARMER FIELD SCHOOLS (WITH AND WITHOUT FFS) FOR SORGHUM PRODUCTION

NAME OF PFGs: UKOMBOZI – SOMANDA VILLAGE -MASWA DISTRICT COUNCIL

| REVENUE | UNIT | WITH FFS | WITHOUT FFS |
| --- | --- | --- | --- |
| Yield Post Harvest loss (12.5%) Net Yield Selling price Total Revenue | Kg./ Ha Kg./ Ha Kg./Ha Tshs/Ha Tshs/ Ha | 1500 187.5 1312.5 225/= 295,312.50/= | 825 103 722 225/= 162,450/= |
| Total cost | Tshs/Ha | 362,500/= | 92,500/= |
| Net cost Revenue | Tshs / Ha | -67,187.50/= | 69,950/= |
| Cost: Benefit Ratio |  | 1:-0.2 | 1: 0.8 |
| Increase in Yield | % | 81.8 | - |
| Break – Even price |  | 0.8 | 1:1.8 |

Source: M &E surveys, June 2008: Maswa District Council

Annex II Success Story: 	Improving cotton storage and Increasing Crop quality.

Mandela village is situated about 38 km. North of Maswa headquarter. The village is among of 30 villages where DASIP is collaborating with community to increase agricultural productivity and income of the rural poor farmers in the village.

The village is prominent for cattle keeping like cows, goats and cultivation of food and cash crops like maize, groundnuts, sweet potatoes, sorghum, sunflower and cotton.

In the past cotton growers did not have any cotton storage facility so they used their available village buildings like village office, resident houses to store cotton before transported to ginneries at Shinyanga. They later realized the importance of having cotton storage facility for storing cotton after harvest. This was revealed in the O&OD exercise that was conducted in year 2005/06 which ranked construction of cotton storage facility as their first priority. This activity was incorporated in their VADPs and was financed by DASIP under ‘quick win’ arrangement in year 2006/07.

Tendering  works started in year 2007 but due to difficulties in acquiring bidders the construction works started end of June in year 2008 and completed in early of July the same year and is now in use not only by the community at Mandela village, but at neighboring villages of Buhungukila and Seng’wa.

The community has formed a strong supervision committee which overseas O&M of the structure. For the case of sustainability the supervision committee at the village has opened account at NMB Maswa branch. To raise their funds the structure used to store cotton by contract manner.

Mr. Dastan who is a chairperson at Mandela village and at the same time   a Cotton grower on behalf of his community witnessed that the structure is now among the source of funds at the village. The promising and significant point explained by chairperson is the commitment made that every member of the village will be much aware to the use of the structure.

Mr. Jilungu who is a hamlet chairperson added that DASIP has done well to finance the construction of the structure because the life standard of Mandela people will change if these funds will be used wisely.

The community showed their satisfactions to the services they are getting are more optimistic that the problem of storing cotton now is greatly solved.

This success story prepared

By  DMEO – MASWA.

Annex III A TABLE MATRIX SHOWN PARTICIPATORY FARMER GROUPS FORMED FY. 2008/09

| S/N | WARD | S/N | VILLAGE | S/N | GROUP NAME | SEX |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Male | Female | TATOL |
| 1 | NYALIKUNGU | 1 | Iyogelo | 1 | Ngwinula | 14 | 7 | 21 |
|  |  |  |  | 2 | Mwakaleka | 6 | 7 | 13 |
|  |  |  |  | 3 | Mwanyomba | 8 | 3 | 11 |
|  |  |  |  | 4 | Gugalama A | 12 | 8 | 20 |
|  |  |  |  | 5 | Ujamaa | 14 | 1 | 15 |
|  |  |  |  | 6 | Balimi ‘A’ |  |  |  |
| 2 | SUKUMA | 2 | Mwabayanda(M) | 7 | Nguvu Kazi |  |  |  |
|  |  |  |  | 8 | Jikomboe na Maji |  |  |  |
|  |  |  |  | 9 | Kisauma Group |  |  |  |
|  |  |  |  | 10 | Umoja ni nguvu | 9 | 9 | 18 |
|  |  |  |  | 11 | Umoja | 9 | 12 | 21 |
|  |  |  |  | 12 | Catholic Group | 12 | 13 | 25 |
|  |  | 3 | Hinduki | 13 | Uvumilivu | 20 | 12 | 32 |
|  |  |  |  | 14 | Tumaini | 15 | 9 | 24 |
|  |  |  |  | 15 | Wajelajela | 6 | 9 | 15 |
|  |  |  |  | 16 | Ujamaa | 11 | 8 | 19 |
|  |  |  |  | 17 | Igembesabo | 9 | 16 | 25 |
|  |  |  |  | 18 | Umoja ni Nguvu | 14 | 11 | 25 |
| 3 | NGULIGULI | 4 | Mwashegeshi | 19 | Wachapakazi | 9 | 12 | 21 |
|  |  |  |  | 20 | Muungano | 6 | 10 | 16 |
|  |  |  |  | 21 | Twende Mbele | 8 | 6 | 14 |
|  |  |  |  | 22 | Ilonganzala | 14 | 13 | 27 |
|  |  |  |  | 23 | Igembesabo | 16 | 9 | 25 |
|  |  |  |  | 24 | Mkombozi | 6 | 13 | 19 |
| 4 | IPILILO | 5 | Mwakabeya | 25 | Maendeleo | 12 | 3 | 15 |
|  |  |  |  | 26 | Upendo |  |  |  |
|  |  |  |  | 27 | Juhudi | 11 | 4 | 15 |
|  |  |  |  | 28 | Bagogo | 6 | 5 | 11 |
|  |  |  |  | 29 | Mwamko |  |  |  |
|  |  |  |  | 30 | Majaliwa |  |  |  |
|  |  | 6 | Ikungulyankoma | 31 | Smart |  |  |  |
|  |  |  |  | 32 | Mapambano |  |  |  |
|  |  |  |  | 33 | Uamusho |  |  |  |
|  |  |  |  | 34 | Tuinue Maisha | 7 | 17 | 24 |
|  |  |  |  | 35 | Maboresho | 10 | 10 | 20 |
|  |  |  |  | 36 | Mshikamano | 17 | 9 | 26 |
| 5 | MPINDO | 7 | Senani | 37 | Upendo | 5 | 7 | 12 |
|  |  |  |  | 38 | Amani ‘B’ | 10 | 11 | 21 |
|  |  |  |  | 39 | Mwaelia | 12 | 13 | 25 |
|  |  |  |  | 40 | Amani ‘A’ |  |  |  |
|  |  |  |  | 41 | Vumilia |  |  |  |
|  |  |  |  | 42 | Imalamakoye | 5 | 9 | 14 |
|  |  | 8 | Somanda | 43 | Igembesabo | 7 | 10 | 17 |
|  |  |  |  | 44 | Balimi | 20 | 6 | 26 |
|  |  |  |  | 45 | Muungano | 12 | 13 | 25 |
|  |  |  |  | 46 | Ushirikiano |  |  |  |
|  |  |  |  | 47 |  |  |  |  |
|  |  |  |  | 48 |  |  |  |  |
|  |  | 9 | Tamanu | 49 | Maendeleo | 16 | 1 | 17 |
|  |  |  |  | 50 | Mkombozi Group | 11 | 4 | 15 |
|  |  |  |  | 51 | Mshikamano | 4 | 11 | 15 |
|  |  |  |  | 52 | Umoja Group | 9 | 6 | 15 |
|  |  |  |  | 53 | Ushirikiano | 11 | 4 | 15 |
|  |  |  |  | 54 | Azimio Group |  |  |  |
| 6 | DAKAMA | 10 | Mwandete | 55 | Azimio | 3 | 21 | 24 |
|  |  |  |  | 56 | Upendo | 7 | 18 | 25 |
|  |  |  |  | 57 | Neema Group | 10 | 9 | 19 |
|  |  |  |  | 58 | Tuleane |  |  |  |
|  |  |  |  | 59 | Ujamaa |  |  |  |
|  |  |  |  | 60 |  |  |  |  |
| 7 | LALAGO | 11 | Mwakidiga | 61 | Azimio |  |  |  |
|  |  |  |  | 62 | Mwabuta |  |  |  |
|  |  |  |  | 63 | Tuwezeshane |  |  |  |
|  |  |  |  | 64 | Ukombozi | 8 | 10 | 18 |
|  |  |  |  | 65 | Kilimifu | 11 | 15 | 26 |
|  |  |  |  | 66 | Buhemba | 11 | 8 | 19 |
| 8 | BUSILILI | 12 | Bushitala | 67 | Tupendane | 21 | 4 | 25 |
|  |  |  |  | 68 | Tubadilike | 10 | 9 | 19 |
|  |  |  |  | 69 | Hekima |  |  |  |
|  |  |  |  | 70 | Neema |  |  |  |
|  |  |  |  | 71 |  |  |  |  |
|  |  |  |  | 72 |  |  |  |  |
|  |  | 13 | Buhungukila | 73 | Merelani | 8 | 5 | 13 |
|  |  |  |  | 74 | Mamba Wimate | 8 | 7 | 15 |
|  |  |  |  | 75 | Senegal | 10 | 3 | 13 |
|  |  |  |  | 76 | Walengwa | 10 | 7 | 17 |
|  |  |  |  | 77 | Mkombozi |  |  |  |
|  |  |  |  | 78 | Mtakuja B |  |  |  |
| 9 | BUDEKWA | 14 | Mwabaraturu | 79 | Nyalusanga |  |  |  |
|  |  |  |  | 80 | Nyota ya Wakulima | 8 | 6 | 14 |
|  |  |  |  | 81 | Nuru Group | 9 | 6 | 15 |
|  |  |  |  | 82 | Ushirika Group | 13 | 5 | 18 |
|  |  |  |  | 83 | Boroboro | 20 | 5 | 25 |
|  |  |  |  | 84 | Vumilia | 14 | 12 | 26 |
| 10 | MASELA | 15 | Mwabomba | 85 | African Inland Church(AIC) | 10 | 5 | 15 |
|  |  |  |  | 86 | Tumaini |  |  |  |
|  |  |  |  | 87 | Amani |  |  |  |
|  |  |  |  | 88 | Maendeleo |  |  |  |
|  |  |  |  | 89 | Moto jembe | 10 | 5 | 15 |
|  |  |  |  | 90 | Igembesabo |  |  |  |
|  |  | 16 | Mandela | 91 | Zinduka Group |  |  |  |
|  |  |  |  | 92 | Bukande A |  |  |  |
|  |  |  |  | 93 | Jidulu | 9 | 6 | 15 |
|  |  |  |  | 94 | Mafanikio | 15 | 10 | 25 |
|  |  |  |  | 95 | Upendo | 10 | 5 | 15 |
|  |  |  |  | 96 | Balimi B |  |  |  |
| 11 | ISANGA | 17 | Isanga | 97 | Upendo | 5 | 5 | 10 |
|  |  |  |  | 98 | MT. Benedicto | 12 | 18 | 30 |
|  |  |  |  | 99 | Jitegemee | 9 | 9 | 18 |
|  |  |  |  | 100 | Viwawa |  |  |  |
|  |  |  |  | 101 | Fatima | 4 | 17 | 21 |
|  |  |  |  | 102 | Nanonano |  |  |  |
|  |  | 18 | Kidema | 103 | Mkombozi | 8 | 12 | 20 |
|  |  |  |  | 104 | Upendo | 12 | 6 | 18 |
|  |  |  |  | 105 | Tubadilike | 4 | 6 | 10 |
|  |  |  |  | 106 | Igembesabo |  |  |  |
|  |  |  |  | 107 | Upendo2 |  |  |  |
|  |  |  |  | 108 | Ujamaa |  |  |  |
| 12 | KULIMI | 19 | Mwamihanza | 109 | Igembesabo |  |  |  |
|  |  |  |  | 110 | Azimio |  |  |  |
|  |  |  |  | 111 | Mapambano | 13 | 5 | 18 |
|  |  |  |  | 112 | Chapa Kazi | 7 | 11 | 18 |
|  |  |  |  | 113 | Maendeleo Supamagembe | 9 | 10 | 19 |
|  |  |  |  | 114 | Maendeleo | 8 | 8 | 16 |
|  |  | 20 | Mwabayanda (S) | 115 | Kandokando | 21 | 4 | 25 |
|  |  |  |  | 116 | Igembesabo | 17 | 8 | 25 |
|  |  |  |  | 117 | Ukombozi | 14 | 11 | 25 |
|  |  |  |  | 118 | Upendo Group | 19 | 6 | 25 |
|  |  |  |  | 119 | Kujitolea |  |  |  |
|  |  |  |  | 120 | Mabatini |  |  |  |
| 13 | BADI | 21 | Nyashimba (S) | 121 | Italemoto | 13 | 12 | 25 |
|  |  |  |  | 122 | Ujamaa | 14 | 4 | 18 |
|  |  |  |  | 123 | Mwamko |  |  |  |
|  |  |  |  | 124 | Mwanzo mgumu | 3 | 22 | 25 |
|  |  |  |  | 125 | Hurumia |  |  |  |
|  |  |  |  | 126 | Tupendane |  |  |  |
|  |  | 22 | Ikungu | 127 | Mshikamano |  |  |  |
|  |  |  |  | 128 | Akina Mama |  |  |  |
|  |  |  |  | 129 | Tuvumilie |  |  |  |
|  |  |  |  | 130 | Mapambano |  |  |  |
|  |  |  |  | 131 |  |  |  |  |
|  |  |  |  | 132 |  |  |  |  |
| 14 | MALAMPAKA | 23 | Nyabubinza | 133 | Changanyikeni |  |  |  |
|  |  |  |  | 134 | Ikonga Balimi |  |  |  |
|  |  |  |  | 135 |  |  |  |  |
|  |  |  |  | 136 |  |  |  |  |
|  |  |  |  | 137 |  |  |  |  |
|  |  |  |  | 138 |  |  |  |  |
| 15 | NYABUBINZA | 24 | Mwabagalu | 139 | Igalukilo | 8 | 7 | 15 |
|  |  |  |  | 140 | Mpakani Group | 7 | 6 | 13 |
|  |  |  |  | 141 | Umoja | 7 | 10 | 17 |
|  |  |  |  | 142 | Ikolaboro |  |  |  |
|  |  |  |  | 143 | Amani Group | 8 | 14 | 22 |
|  |  |  |  | 144 | Ukombozi | 13 | 7 | 20 |
|  |  | 25 | Zawa | 145 | Mkombozi | 9 | 13 | 22 |
|  |  |  |  | 146 | Basukamagembe | 8 | 7 | 15 |
|  |  |  |  | 147 | Luchibila makoye | 8 | 7 | 15 |
|  |  |  |  | 148 | Maisha Bora | 11 | 14 | 25 |
|  |  |  |  | 149 | Mwabageni | 6 | 8 | 14 |
|  |  |  |  | 150 | Upendo | 5 | 14 | 19 |
| 16 | SHISHIYU | 26 | Jija | 151 | Uhuru Jamii | 8 | 9 | 17 |
|  |  |  |  | 152 | Tupendane | 14 | 9 | 23 |
|  |  |  |  | 153 | Washirika | 4 | 7 | 11 |
|  |  |  |  | 154 | Upendo | 13 | 4 | 17 |
|  |  |  |  | 155 | RC Group | 8 | 13 | 21 |
|  |  |  |  | 156 | Chapakazi Jamii | 13 | 8 | 21 |
|  |  | 27 | Igunya | 157 | Yataka Moyo | 21 | 3 | 24 |
|  |  |  |  | 158 | Tupendane | 19 | 5 | 25 |
|  |  |  |  | 159 | Twende Pamoja | 14 | 6 | 20 |
|  |  |  |  | 160 | Umoja ni Nguvu | 5 | 10 | 15 |
|  |  |  |  | 161 | Amani |  |  |  |
|  |  |  |  | 162 |  |  |  |  |
| 17 | KADOTO | 28 | Malekano | 163 | Uzalishaji | 10 | 7 | 17 |
|  |  |  |  | 164 | Sauti ya Mnyonge | 7 | 7 | 14 |
|  |  |  |  | 165 | Tumaini | 16 | 6 | 22 |
|  |  |  |  | 166 | Muamini | 16 | 9 | 25 |
|  |  |  |  | 167 | Upendo |  |  |  |
|  |  |  |  | 168 | Tupendane |  |  |  |
| 18 | BUCHAMBI | 29 | Kinamwigulu | 169 | Songambele | 12 | 8 | 20 |
|  |  |  |  | 170 | Ngoshagugema | 13 | 7 | 20 |
|  |  |  |  | 171 | Yanga Vijana B | 19 | 6 | 25 |
|  |  |  |  | 172 | Chapakazi | 7 | 6 | 13 |
|  |  |  |  | 173 | Vijana Songambele | 13 | 6 | 19 |
|  |  |  |  | 174 |  | 13 | 6 | 19 |
|  |  | 30 | Mwabujiku | 175 | Kujitegemea |  |  |  |
|  |  |  |  | 176 | Tumaini | 17 | 13 | 30 |
|  |  |  |  | 177 |  |  |  |  |
|  |  |  |  | 178 |  |  |  |  |
|  |  |  |  | 179 |  |  |  |  |
|  |  |  |  | 180 |  |  |  |  |
| TOTAL |  |  |

ANNEX IV (a) FUNDS TRANSFERRED TO PFGs  FORMED FY 2007/08

| NO | NAME OF PARTICIPATORY FARMER GROUP | NAME OF VILLAGE | A/C NO. | AMOUNT TO BE TRANSFERED |
| --- | --- | --- | --- | --- |
| 1 | Senani Group | Senani | 3081600238 | 400,000 |
| 2 | Walalasagala | Senani | 3082300556 | 400,000 |
| 3 | Maendeleo Tumbili | Mwandete | 3081600437 | 400,000 |
| 4 | Nuru Group | Mwabayanda (M) | 3082302590 | 400,000 |
| 5 | Kiwaki | Mwabayanda (M) | 3082300264 | 400,000 |
| 6 | Faraja | Buhungukila | 3081600388 | 400,000 |
| 7 | Kasi Mpya | Mwashegeshi | 3081100084 | 400,000 |
| 8 | Mwalundi | Malekano | 3082300617 | 400,000 |
| 9 | Jerusalem | Mwakidiga | 3081100086 | 400,000 |
| 10 | Tuamke | Mwakidiga | 3081100087 | 400,000 |
| 11 | Amani | Mwandete | 3081100093 | 400,000 |
| 12 | Ufugaji Nyuki | Isanga | 3081100085 | 400,000 |
| 13 | Mazingira | Isanga | 3082300521 | 400,000 |
| 14 | Mshikamano | Hinduki | 3082300532 | 400,000 |
| 15 | Upendo | Hinduki | 3082300426 | 400,000 |
| 16 | Mshikamano | Nyashimba (S) | 3081600227 | 400,000 |
| 17 | Tumaini Group | Mwabaraturu | 3081300012 | 400,000 |
| 18 | Chapakazi | Mwabagalu | 3082300637 | 400,000 |
| 19 | Matengenezo | Mwakabeya | 3082300639 | 400,000 |
| 20 | Tumaini | Nyabubinza | 3082300640 | 400,000 |
| 21 | Isabilo | Mwabayanda (S) | 3082300647 | 400,000 |
| 22 | Mshitue | Ikungulyankoma | 3082300648 | 400,000 |
| 23 | Mshikamano | Iyogelo | 3082300668 | 400,000 |
| 24 | Igembesabo | Igunya | 3082300672 | 400,000 |
| 25 | Iloganzala | Mwabagalu | 3082300680 | 400,000 |
| 26 | Jikwamue | Mwabayanda(S) | 3082300655 | 400,000 |
| 27 | Tupendane | Mwakabeya | 3082300669 | 400,000 |
| 28 | Ipejanzala | Zawa | 3082300659 | 400,000 |
| 29 | MT. Maria | Kidema | 3082300696 | 400,000 |
| 30 | Wakuji | Jija | 3082300695 | 400,000 |
| 31 | Wasimbangobi | Jija | 3082300697 | 400,000 |
| 32 | Kazi ni Moyo | Igunya | 3082300664 | 400,000 |
| 33 | Igembesabo | Mwamihanza | 3081300022 | 400,000 |
| 34 | Nguvu Mpya | Mwashegeshi | 3082300684 | 400,000 |
| 35 | Umoja | Kinamwigulu | 3082300657 | 400,000 |
| 36 | Nguvu Kazi | Mwabomba | 3082300548 | 400,000 |
| 37 | Mapinduzi | Kinamwigulu | 3082300710 | 400,000 |
| 38 | MT. Joseph | Kidema | 3082300709 | 400,000 |
| 39 | Mapinduzi | Bushitala | 3082300712 | 400,000 |
| 40 | Mshikamano Group | Mwabujiku | 3082300724 | 400,000 |
| 41 | Chapakazi | Mwabujiku | 3082300737 | 400,000 |
| 42 | Mtapenda Group | Zawa | 3082300745 | 400,000 |
| 43 | Muungano | Mwamihanza | 3082300753 | 400,000 |
| 44 | Akina mama mkombozi | Mandela | 3082300453 | 400,000 |
|  | TOTAL |  |  | 17,600,000 |

ANNEX IV (b) FUNDS TRANSFERRED TO NEWLY FORMED PFGs FY 2008/09

| NO | NAME OF PARTICIPATORY FARMER GROUP | NAME OF VILLAGE | A/C NO. | AMOUNT TO BE TRANSFERRED |
| --- | --- | --- | --- | --- |
| 1 | Upendo | Senani | 3082300301 | 500,000 |
| 2 | Amani ‘ B’ | Senani | 3082300634 | 500,000 |
| 3 | Mwaelia | Senani | 3082300636 | 500,000 |
| 4 | Amani ‘ A ‘ | Senani | 3082300635 | 500,000 |
| 5 | Uvumilivu | Hinduki | 3082300638 | 500,000 |
| 6 | Tumaini | Hinduki | 3081600641 | 500,000 |
| 7 | Wachapakazi | Mwashegeshi | 3082300642 | 500,000 |
| 8 | Muungano | Mwashegeshi | 3082300643 | 500,000 |
| 9 | Smart | Ikungulyankoma | 3082300644 | 500,000 |
| 10 | Mapambano | Ikungulyankoma | 3082300646 | 500,000 |
| 11 | Azimio | Mwandete | 3082300365 | 500,000 |
| 12 | Vumilia | Senani | 3082300561 | 500,000 |
| 13 | Imalamakoye | Senani | 3082300313 | 500,000 |
| 14 | Kandokando | Mwabayanda(S) | 3082300650 | 500,000 |
| 15 | Igembesabo | Mwabayanda(S) | 3082300652 | 500,000 |
| 16 | Maendeleo | Tamanu | 3082300656 | 500,000 |
| 17 | Twende mbele | Mwashegeshi | 3082300653 | 500,000 |
| 18 | Uhuru Jamii | Jija | 3082300654 | 500,000 |
| 19 | Igalukilo | Mwabagalu | 3082300658 | 500,000 |
| 20 | Tupendane | Jija | 3082300689 | 500,000 |
| 21 | Nguvukazi | Mwabayanda(M) | 3082300660 | 500,000 |
| 22 | Upendo | Isanga | 3082300665 | 500,000 |
| 23 | MT. Benedicto | Isanga | 3082300666 | 500,000 |
| 24 | Kujitegemea | Mwabujiku | 3082300663 | 500,000 |
| 25 | Azimio | Mwamihanza | 3082300661 | 500,000 |
| 26 | Mkombozi | Zawa | 3082300662 | 500,000 |
| 27 | Mkombozi Group | Tamanu | 3082300670 | 500,000 |
| 28 | Mpakani Group | Mwabagalu | 3082300675 | 500,000 |
| 29 | Italemoto | Nyashimba (S) | 3082300674 | 500,000 |
| 30 | Umoja | Mwabagalu | 3082300673 | 500,000 |
| 31 | Mshikamano Group | Tamanu | 3082300677 | 500,000 |
| 32 | Umoja Group | Tamanu | 3082300678 | 500,000 |
| 33 | Zinduka Group | Mandela | 3082300676 | 500,000 |
| 34 | Ngoshagugema | Kinamwigulu | 3082300679 | 500,000 |
| 35 | Ikolaboro | Mwabagalu | 3082300681 | 500,000 |
| 36 | Jikomboe na Maji | Mwabayanda (M) | 3082300683 | 500,000 |
| 37 | Mapambano | Mwamihanza | 3082300685 | 500,000 |
| 38 | Mshikamano | Ikungu | 3082300682 | 500,000 |
| 39 | Igembesabo | Mwashegeshi | 3082300686 | 500,000 |
| 40 | Uamusho | Ikungulyankoma | 3082300687 | 500,000 |
| 41 | Azimio Group | Tamanu | 3082300690 | 500,000 |
| 42 | Tuinue Maisha | Ikungulyankoma | 3082300691 | 500,000 |
| 43 | Ukombozi | Mwabayanda (S) | 3082300692 | 500,000 |
| 44 | Jitegemee | Isanga | 3082300698 | 500,000 |
| 45 | Washirika | Jija | 3082300699 | 500,000 |
| 46 | Ushirikiano | Tamanu | 3082300694 | 500,000 |
| 47 | Igembesabo | Somanda | 3082300693 | 500,000 |
| 48 | Ukombozi | Mwabagalu | 3082300700 | 500,000 |
| 49 | Amani Group | Mwabagalu | 3082300701 | 500,000 |
| 50 | Upendo Group | Mwandete | 3082300702 | 500,000 |
| 51 | Basukamagembe | Zawa | 3082300703 | 500,000 |
| 52 | Upendo Group | Mwabayanda (S) | 3082300705 | 500,000 |
| 53 | Twende Pamoja | Igunya | 3082300707 | 500,000 |
| 54 | Neema Goup | Mwandete | 3082300649 | 500,000 |
| 55 | Fatima | Isanga | 3082300713 | 500,000 |
| 56 | Luchibula Makoye | Zawa | 3082300711 | 500,000 |
| 57 | Chapakazi | Kinamwigulu | 3082300715 | 500,000 |
| 58 | Upendo | Kidema | 3082300714 | 500,000 |
| 59 | Maendeleo | Mwakabeya | 3082300718 | 500,000 |
| 60 | Upendo | Mwakabeya | 3082300719 | 500,000 |
| 61 | Juhudi | Mwakabeya | 3082300716 | 500,000 |
| 62 | RC Group | Jija | 3082300717 | 500,000 |
| 63 | Chapakazijamii Group | Jija | 3082300720 | 500,000 |
| 64 | Umoja ni nguvu | Mwabayanda (M) | 3082300723 | 500,000 |
| 65 | Tumaini | Mwabujiku | 3082300722 | 500,000 |
| 66 | Mwamko | Nyashimba(S) | 3082300726 | 500,000 |
| 67 | Mwanzo mgumu | Nyashimba(S) | 3082300725 | 500,000 |
| 68 | Tumaini | Mwabomba | 3082300727 | 500,000 |
| 69 | Motojembe | Mwabomba | 3082300728 | 500,000 |
| 70 | Muungano | Nyashimba(S) | 3082300730 | 500,000 |
| 71 | Amani | Mwabomba | 3082300729 | 500,000 |
| 72 | Maboresho | Ikungulyankoma | 3082300733 | 500,000 |
| 73 | Mafanikio | Mandela | 3082300735 | 500,000 |
| 74 | Jidulu | Mandela | 3082300734 | 500,000 |
| 75 | Vijanasngambele | Kinamwigulu | 3082300736 | 500,000 |
| 76 | Maendeleo | Mwabomba | 3082300738 | 500,000 |
| 77 | Mkombozi | Mwashegeshi | 3082300739 | 500,000 |
| 78 | Mkombozi | Buhungukila | 3082300741 | 500,000 |
| 79 | Iloganzala | Mwashegeshi | 3082300740 | 500,000 |
| 80 | Yanga vijana “B” | Kinamwigulu | 3082300744 | 500,000 |
| 81 | Umoja | Mwabayanda (M) | 3082300746 | 500,000 |
| 82 | Mtakuja “B” | Buhungukila | 3082300750 | 500,000 |
| 83 | Walengwa | Buhungukila | 3082300751 | 500,000 |
| 84 | Maendeleo | Mwamihanza | 3082300752 | 500,000 |
| 85 | Catholic Group | Mwabayanda (M) | 3082300749 | 500,000 |
| 86 | Mapambano | Ikungu | 3082300825 | 500,000 |
| 87 | Mkombozi | Kidema | 3082300757 | 500,000 |
| 88 | Igembesabo | Mwabomba | 3082300754 | 500,000 |
| 89 | Upendo | Zawa | 3082300755 | 500,000 |
| 90 | African Inland Church | Mwabomba | 3082300756 | 500,000 |
|  | TOTAL |  |  | 45,000,000 |